## Sheet1
Order | Description | Technical Object | Technical Object Description | Location | Location Name | Start Date | End Date | Main Work Center | Main Work Center Name | Created On | Created By | Created by User Name | System Condition | System Condition Text | Person Responsible | Person Responsible Name | Subphase | Subphase Description | Cost Estimated / Planned / Actual | Order Status | Order Status Description | Order Type | Order Type Text | Notification | Notification Description | Priority | Priority Text | Processing Context | Short Description | Week Number | Start_Date
1200002477 | FILTR CHGES OFFICES ABOVE MAINT-W-4 | HIN-100-030-020-040 | HEATING VENTILATING & AIR CONDITIONING | BLEACH | Bleach | 25.06.2025 | 25.06.2025 | PM_I_HVA | Heating Ventilation Air Condition | 04.06.2025 | IP1020250604 |  | 1 | in operation | 91100020 | Carl Redahl | 85 | TECO | 0.00 / 194.00 / 194.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002517 | FILTR CHGES OFFICES ABOVE MAINT-W-4 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 25.06.2025
1200002667 | CARPENTER SHOP BI-WEEKLY AUDIT | HIN-100-030-020-010 | GENERAL TRADES SHOP EQUIPMENT | BLEACH | Bleach | 23.06.2025 | 23.06.2025 | PM_I_CA | Carpenter | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 194.00 / 485.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002587 | CARPENTER SHOP BI-WEEKLY AUDIT | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002677 | BLEACH & R8-LUBE-7 | HIN-030-010 | BLEACH PLANT | BLEACH | Bleach | 23.06.2025 | 23.06.2025 | PM_I_LM | Lube Mechanics | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 70 | Work Started | 0.00 / 970.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002597 | BLEACH & R8-LUBE-7 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002703 | FL-BLEACH ALL FLOORS | HIN-030-010 | BLEACH PLANT | BLEACH | Bleach | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 388.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002623 | FL-BLEACH ALL FLOORS | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002678 | WEEKLY LUB IN BROWNSTOCK | HIN-020-020 | BROWN STOCK | BROWN | Brownstock | 23.06.2025 | 23.06.2025 | PM_I_LM | Lube Mechanics | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 70 | Work Started | 0.00 / 970.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002598 | WEEKLY LUB IN BROWNSTOCK | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002694 | WEEKLY KAPPA | HIN/038Z1667 | KAPPA ANALYZER | BROWN | Brownstock | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 08.06.2025 | IP1020250608 |  | 1 | in operation | 91100020 | Carl Redahl | 85 | TECO | 0.00 / 194.00 / 776.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002614 | WEEKLY KAPPA | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002708 | FL-BROWN STOCK 2ND FLOOR | HIN-020-020 | BROWN STOCK | BROWN | Brownstock | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 291.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002628 | FL-BROWN STOCK 2ND FLOOR | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002709 | FL-BROWN STOCK 3RD FLOOR | HIN-020-020 | BROWN STOCK | BROWN | Brownstock | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 679.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002629 | FL-BROWN STOCK 3RD FLOOR | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002710 | FL-BROWN STOCK GROUND FLOOR | HIN-020-020 | BROWN STOCK | BROWN | Brownstock | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 582.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002630 | FL-BROWN STOCK GROUND FLOOR | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002711 | FL-BROWN STOCK 4TH FLOOR | HIN-020-020 | BROWN STOCK | BROWN | Brownstock | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 582.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002631 | FL-BROWN STOCK 4TH FLOOR | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002479 | DOG BONE RUBBER INSULATORS - M1 | HIN/034BIN11 | BIN, CHIP | DIGESTER | Digester | 25.06.2025 | 25.06.2025 | PM_I_MW | Millwright | 04.06.2025 | IP1020250604 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 97.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002519 | DOG BONE RUBBER INSULATORS - M1 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 25.06.2025
1200002663 | P-VIB-SOUTH-7 | HIN-020 | DIGESTER / BROWN STOCK | DIGESTER | Digester | 23.06.2025 | 26.06.2025 | PM_I_LM | Lube Mechanics | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 70 | Work Started | 0.00 / 3,880.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002583 | P-VIB-SOUTH-7 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002674 | BLEED & RECHARGE PRESS DIFF ACCUMS-M-1 | HIN/034317 | HYDRAULICS, VALVE STATION | DIGESTER | Digester | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 970.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002594 | BLEED & RECHARGE PRESS DIFF ACCUMS-M-1 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002696 | DIG- WEEKLY LUBE | HIN-020-010-120 | DIGESTER, GENERAL | DIGESTER | Digester | 23.06.2025 | 24.06.2025 | PM_I_LM | Lube Mechanics | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 70 | Work Started | 0.00 / 1,940.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002616 | DIG- WEEKLY LUBE | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002713 | DIG- BASIC CARE ALL FLOORS | HIN-020-010 | DIGESTER | DIGESTER | Digester | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 582.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002633 | DIG- BASIC CARE ALL FLOORS | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002731 | Weekly E/I South Shop Cleanup | HIN-100-030-090-020 | EI SHOPS - SOUTH (EIS) | DIGESTER | Digester | 24.06.2025 | 24.06.2025 | PM_I_EL | Electrical | 10.06.2025 | IP1020250610 |  | 1 | in operation | 91100020 | Carl Redahl | 70 | Work Started | 0.00 / 727.50 / 388.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002671 | Weekly E/I South Shop Cleanup | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 24.06.2025
1200002623 | PURGE-DENSITY-EVAPS 3 EFFECT 1 DENSITY | HIN/051Z6471 | #1 EFFECT DENSITY INDICATION | EVAPS | Evaps/Recovery | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 01.06.2025 | IP1020250601 |  | 1 | in operation | 91100016 | Mike Kerr | 65 | Ready to Execute | 0.00 / 194.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002563 | PURGE-DENSITY-EVAPS 3 EFFECT 1 DENSITY | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002692 | COND-IND - EVAPS 3 SUMP | HIN/051Z6319 | #3 EVAPS SUMP CONDUCTIVITY INDICATION... | EVAPS | Evaps/Recovery | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 08.06.2025 | IP1020250608 |  | 1 | in operation | 91100016 | Mike Kerr | 65 | Ready to Execute | 0.00 / 194.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002612 | COND-IND - EVAPS 3 SUMP | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002717 | BCPM-M-EV-EVAPORATOR #3 | HIN-050-010-020 | BLACK LIQUOR EVAPORATOR SYSTEM # 3 | EVAPS | Evaps/Recovery | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation | 91100108 | Mark Parker | 65 | Ready to Execute | 0.00 / 485.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002637 | BCPM-M-EV-EVAPORATOR #3 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002478 | 63423 AC - KILN PRECOAT STI SHACK | HIN/06342311 | AIR CONDITIONER - KILN STI SHACK | KILN | Lime Kiln | 25.06.2025 | 25.06.2025 | PM_I_HVA | Heating Ventilation Air Condition | 04.06.2025 | IP1020250604 |  | 1 | in operation | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 208.06 / 194.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002518 | 63423 AC - KILN PRECOAT STI SHACK | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 25.06.2025
1200002691 | CEMS - KILN - 2WK | HIN-040-020-090 | KILN, GENERAL | KILN | Lime Kiln | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 08.06.2025 | IP1020250608 |  | 1 | in operation | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 327.63 / 388.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002611 | CEMS - KILN - 2WK | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002716 | PC-PRECOAT BLD ALL FLOORS | HIN-040-020-010 | PRECOAT FILTER SYSTEM | KILN | Lime Kiln | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation | 91100108 | Mark Parker | 85 | TECO | 0.00 / 485.00 / 485.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002636 | PC-PRECOAT BLD ALL FLOORS | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002723 | RK-PLATCO VALVE | HIN/06313111 | VALVE, PLATTCO FEED SILO DISCHARGE | KILN | Lime Kiln | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation | 91100108 | Mark Parker | 85 | TECO | 0.00 / 194.00 / 194.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002643 | RK-PLATCO VALVE | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002661 | 7-JANITORIAL | HIN-090 | MOVERS AND SHAKERS | MOB | Mobile | 23.06.2025 | 26.06.2025 | PM_I_HDM | Heavy Duty Mechanics | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 65 | Ready to Execute | 0.00 / 3,880.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002581 | 7-JANITORIAL | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002669 | GARAGE BI-WEEKLY SHOP AUDITS | HIN-090 | MOVERS AND SHAKERS | MOB | Mobile | 23.06.2025 | 23.06.2025 | PM_I_HDM | Heavy Duty Mechanics | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 65 | Ready to Execute | 0.00 / 194.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002589 | GARAGE BI-WEEKLY SHOP AUDITS | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002681 | WEEKLY STINGER OPERATION | HIN-090-020 | MOBILE EQUIPMENT | MOB | Mobile | 23.06.2025 | 26.06.2025 | PM_I_HDM | Heavy Duty Mechanics | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 65 | Ready to Execute | 0.00 / 3,880.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002601 | WEEKLY STINGER OPERATION | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002683 | CHECK/FILL ENG OIL KILN AUX DRIVE 63-103 | HIN/063103 | NATURAL GAS ENGINE, AUX. MOTOR KILN | MOB | Mobile | 23.06.2025 | 23.06.2025 | PM_I_HDM | Heavy Duty Mechanics | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 80 | Work Done | 0.00 / 97.00 / 97.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002603 | CHECK/FILL ENG OIL KILN AUX DRIVE 63-103 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002688 | WP-WEEKLY GARAGE SHOP CLEAN UP | HIN-100-040-030 | BUILDINGS, MILL GARAGE | MOB | Mobile | 23.06.2025 | 23.06.2025 | PM_I_HDM | Heavy Duty Mechanics | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 65 | Ready to Execute | 0.00 / 1,940.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002608 | WP-WEEKLY GARAGE SHOP CLEAN UP | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002689 | GREASING UNIT & CHECK FOR DEFICIENCIES. | HIN/MOB056 | TRUCK, MILL WASTE DISPOSAL UNIT 381 | MOB | Mobile | 23.06.2025 | 23.06.2025 | PM_I_HDM | Heavy Duty Mechanics | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 65 | Ready to Execute | 0.00 / 194.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002609 | GREASING UNIT & CHECK FOR DEFICIENCIES. | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002704 | COLLECT HOURS ON MOBILE EQUIP | HIN-100-040-020 | MAIN MILL GARAGE GENERAL | MOB | Mobile | 23.06.2025 | 23.06.2025 | PM_I_HDM | Heavy Duty Mechanics | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 194.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002624 | COLLECT HOURS ON MOBILE EQUIP | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002519 | DAY1, WEEK13,BALE LINE RELIABILITY | HIN-060-030-170 | BALE LINE B | MR | Machine Room | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 25.05.2025 | IP1020250525 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 97.00 / 97.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002469 | DAY1, WEEK13,BALE LINE RELIABILITY | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002520 | (WR) DAY2, WEEK13,BALE LINE RELIABILITY | HIN-060-030-170 | BALE LINE B | MR | Machine Room | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 25.05.2025 | IP1020250525 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 232.80 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002470 | (WR) DAY2, WEEK13,BALE LINE RELIABILITY | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002521 | DAY3, WEEK13,BALE LINE RELIABILITY | HIN-060-030-170 | BALE LINE B | MR | Machine Room | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 25.05.2025 | IP1020250525 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 97.00 / 97.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002471 | DAY3, WEEK13,BALE LINE RELIABILITY | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002522 | DAY4, WEEK13,BALE LINE RELIABILITY | HIN-060-030-170 | BALE LINE B | MR | Machine Room | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 25.05.2025 | IP1020250525 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 97.00 / 97.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002472 | DAY4, WEEK13,BALE LINE RELIABILITY | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002666 | MR MAINT SHOP BI-WEEKLY AUDIT | HIN-060 | MACHINE ROOM | MR | Machine Room | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 388.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002586 | MR MAINT SHOP BI-WEEKLY AUDIT | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002671 | WEEKLY SCANNER CHECK & CLEANING | HIN/050Z3656 | BASIS WEIGHT DRY END | MR | Machine Room | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 65 | Ready to Execute | 0.00 / 194.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002591 | WEEKLY SCANNER CHECK & CLEANING | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002672 | PPM SHOP BI-WEEKLY AUDIT | HIN-100-030-060-020 | MACHINE ROOM MAINT SHOP GENERAL | MR | Machine Room | 23.06.2025 | 23.06.2025 | PM_I_LM | Lube Mechanics | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 65 | Ready to Execute | 0.00 / 194.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002592 | PPM SHOP BI-WEEKLY AUDIT | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002675 | MACHINE-LUBE-7 | HIN-060 | MACHINE ROOM | MR | Machine Room | 23.06.2025 | 25.06.2025 | PM_I_LM | Lube Mechanics | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 65 | Ready to Execute | 0.00 / 2,910.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002595 | MACHINE-LUBE-7 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002702 | WEEKLY ODI CLEANING & CAL | HIN/050Z3656 | BASIS WEIGHT DRY END | MR | Machine Room | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 08.06.2025 | IP1020250608 |  | 1 | in operation | 91100020 | Carl Redahl | 65 | Ready to Execute | 0.00 / 174.60 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002622 | WEEKLY ODI CLEANING & CAL | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002706 | MR-BOTTOM FLOOR | HIN-060 | MACHINE ROOM | MR | Machine Room | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 679.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002626 | MR-BOTTOM FLOOR | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002707 | MR-SECOND FLOOR | HIN-060 | MACHINE ROOM | MR | Machine Room | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 582.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002627 | MR-SECOND FLOOR | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002676 | PULP WAREHOUSE-LUBE-7 | HIN-070 | PULP WAREHOUSE | PLPWRHSE | Pulp Warehouse | 23.06.2025 | 23.06.2025 | PM_I_LM | Lube Mechanics | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 65 | Ready to Execute | 0.00 / 970.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002596 | PULP WAREHOUSE-LUBE-7 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002705 | EL_UNITYER PRINTERS_WEEKLY RR | HIN/071217 | PRINTERS, UNITYER NORTH ARM, A-LINE | PLPWRHSE | Pulp Warehouse | 23.06.2025 | 23.06.2025 | PM_I_EL | Electrical | 08.06.2025 | IP1020250608 |  | 1 | in operation | 91100020 | Carl Redahl | 65 | Ready to Execute | 0.00 / 97.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002625 | EL_UNITYER PRINTERS_WEEKLY RR | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002679 | PR- WKLY LUB IN P&R | HIN-050-020 | RECOVERY BOILER SYSTEMS | PRECIPS | Precips | 23.06.2025 | 26.06.2025 | PM_I_LM | Lube Mechanics | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 80 | Work Done | 0.00 / 3,880.00 / 5,616.03 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002599 | PR- WKLY LUB IN P&R | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002690 | CEMS - RB2, RB3, MAIN STACK - 2WK | HIN-050-020 | RECOVERY BOILER SYSTEMS | PRECIPS | Precips | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 08.06.2025 | IP1020250608 |  | 1 | in operation | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 982.89 / 679.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002610 | CEMS - RB2, RB3, MAIN STACK - 2WK | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002625 | PR-TRV_GRATE-W | HIN-050-040-040-070 | GRATES, TRAVELING # 3 POWER BOILER | PRWBOILER | Power Boilers | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 01.06.2025 | IP1020250601 |  | 1 | in operation | 91100108 | Mark Parker | 65 | Ready to Execute | 0.00 / 194.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002565 | PR-TRV_GRATE-W | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002719 | ANALYTL-INDICAT-DEMIN WTR-DEMIN STRGE PH | HIN/056Z7976 | DEMIN WATER TO STORAGE PH INDICATION | PRWBOILER | Power Boilers | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 08.06.2025 | IP1020250608 |  | 1 | in operation | 91100016 | Mike Kerr | 65 | Ready to Execute | 0.00 / 242.50 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002639 | ANALYTL-INDICAT-DEMIN WTR-DEMIN STRGE PH | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002783 | Weekly E/I North Shop Cleanup | HIN-100-030-090-010 | EI SHOPS - NORTH (EIN) | PRWBOILER | Power Boilers | 26.06.2025 | 26.06.2025 | PM_I_EL | Electrical | 12.06.2025 | IP1020250612 |  | 1 | in operation | 91100016 | Mike Kerr | 65 | Ready to Execute | 0.00 / 727.50 / 46.71 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002693 | Weekly E/I North Shop Cleanup | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 26.06.2025
1200002641 | LOOP 7605-WTR TO MOL SLAKR BOWL/CLASSIF | HIN/061Z7605 | WATER TO MILK OF LIME SLAKER FLOW CON... | RECAUST | Recaust | 25.06.2025 | 25.06.2025 | PM_I_IN | Instrumentation | 04.06.2025 | IP1020250604 |  | 1 | in operation | 91100016 | Mike Kerr | 65 | Ready to Execute | 0.00 / 194.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002571 | LOOP 7605-WTR TO MOL SLAKR BOWL/CLASSIF | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 25.06.2025
1200002670 | -BI-WEEKLY CPC AUDIT | HIN-040 | RECAUST AND KILN | RECAUST | Recaust | 23.06.2025 | 23.06.2025 | PM_I_WE | Welders | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 97.00 / 97.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002590 | -BI-WEEKLY CPC AUDIT | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002673 | RECAUST LUBE WEEKLY | HIN-040-010 | RECAUST SYSTEMS | RECAUST | Recaust | 23.06.2025 | 25.06.2025 | PM_I_LM | Lube Mechanics | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 80 | Work Done | 0.00 / 2,910.00 / 2,910.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002593 | RECAUST LUBE WEEKLY | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002697 | BI-WEEKLY, TIN SHOP AUDIT | HIN-040 | RECAUST AND KILN | RECAUST | Recaust | 23.06.2025 | 23.06.2025 | PM_I_TS | Tin Smith | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 97.00 / 97.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002617 | BI-WEEKLY, TIN SHOP AUDIT | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002715 | RC-RECAUST BASIC CARE ALL FLOORS | HIN-040-010 | RECAUST SYSTEMS | RECAUST | Recaust | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation | 91100108 | Mark Parker | 85 | TECO | 0.00 / 582.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002635 | RC-RECAUST BASIC CARE ALL FLOORS | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002562 | ANALYT-INDICAT-RB3 FLUE GAS CO CONTENT | HIN/052Z6188 | RB #3 STACK GAS CO CONCENTRATION INDI... | RECBOILER | Recovery Boilers | 26.06.2025 | 26.06.2025 | PM_I_IN | Instrumentation | 05.06.2025 | IP1020250605 |  | 1 | in operation | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 194.00 / 97.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002522 | ANALYT-INDICAT-RB3 FLUE GAS CO CONTENT | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 26.06.2025
1200002640 | LEVEL - ALARMS - RB3 AREA SUMP | HIN/052Z6042 | RECOVERY AREA SUMP LEVEL CONTROL | RECBOILER | Recovery Boilers | 25.06.2025 | 25.06.2025 | PM_I_IN | Instrumentation | 04.06.2025 | IP1020250604 |  | 1 | in operation | 91100016 | Mike Kerr | 65 | Ready to Execute | 0.00 / 194.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002570 | LEVEL - ALARMS - RB3 AREA SUMP | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 25.06.2025
1200002664 | P-VIB-NORTH-7 | HIN-050 | POWER AND RECOVERY | RECBOILER | Recovery Boilers | 23.06.2025 | 26.06.2025 | PM_I_LM | Lube Mechanics | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 3,880.00 / 2,910.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002584 | P-VIB-NORTH-7 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002668 | BOILERS MAINT SHOP BI-WEEKLY AUDIT | HIN-050 | POWER AND RECOVERY | RECBOILER | Recovery Boilers | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation | 91100108 | Mark Parker | 85 | TECO | 0.00 / 194.00 / 218.31 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002588 | BOILERS MAINT SHOP BI-WEEKLY AUDIT | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002701 | PB3 8TH FLR RECIRC & VENT FAN FILTRS | HIN/059221 | HVAC - RECIRCULATION & VENTILATION FAN | RECBOILER | Recovery Boilers | 23.06.2025 | 23.06.2025 | PM_I_HVA | Heating Ventilation Air Condition | 08.06.2025 | IP1020250608 |  | 1 | in operation | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 388.00 / 948.75 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002621 | PB3 8TH FLR RECIRC & VENT FAN FILTRS | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002718 | CONDUCTIVITY-INDICATION-REC AREA SUMP | HIN/052Z6043 | RECOVERY AREA SUMP CONDUCTIVITY INDIC... | RECBOILER | Recovery Boilers | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 08.06.2025 | IP1020250608 |  | 1 | in operation | 91100016 | Mike Kerr | 65 | Ready to Execute | 0.00 / 194.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002638 | CONDUCTIVITY-INDICATION-REC AREA SUMP | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002722 | PR-#3 RB-IKS | HIN-050-020-010-100 | BOILER INTERNAL CLEANING SYSTEM | RECBOILER | Recovery Boilers | 23.06.2025 | 24.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation | 91100108 | Mark Parker | 65 | Ready to Execute | 0.00 / 1,940.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002642 | PR-#3 RB-IKS | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002581 | REL-EL-POWERHOUSE-MOTOR GREASING-T3-28D | HIN-050-040-010-050 | ELECTRICAL SERVICE - POWER BOILERS & ... | TURBINES | Turbines | 27.06.2025 | 27.06.2025 | PM_I_LM | Lube Mechanics | 30.05.2025 | IP1020250530 |  | 1 | in operation | 91100016 | Mike Kerr | 65 | Ready to Execute | 0.00 / 97.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002531 | REL-EL-POWERHOUSE-MOTOR GREASING-T3-28D | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 27.06.2025
1200002698 | AIR COMPRESSOR - EFF BLDG | HIN/087173 | COMPRESSOR CLARIFIER AIR SUPPLY | WEFFLUE | Water Effluent | 23.06.2025 | 23.06.2025 | PM_I_EL | Electrical | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 145.50 / 145.50 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002618 | AIR COMPRESSOR - EFF BLDG | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002662 | FSS-LUBE WEEKLY | HIN-010-040-010 | SILO STORAGE AND CONVEYING | WP | Wood Processing | 23.06.2025 | 25.06.2025 | PM_I_LM | Lube Mechanics | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 80 | Work Done | 0.00 / 2,425.00 / 2,525.63 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002582 | FSS-LUBE WEEKLY | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002693 | WP-HOG CONVS BASIC CARE | HIN-010-070 | HOG FUEL HANDLING | WP | Wood Processing | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 388.00 / 388.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002613 | WP-HOG CONVS BASIC CARE | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002695 | ELEC- WEEKLY TRUCK DUMPER CHECKS | HIN/02212204 | CIRCUIT CNTL, MAIN DUMPER DISCHARGE | WP | Wood Processing | 23.06.2025 | 23.06.2025 | PM_I_EL | Electrical | 08.06.2025 | IP1020250608 |  | 1 | in operation | 91100016 | Mike Kerr | 65 | Ready to Execute | 0.00 / 194.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002615 | ELEC- WEEKLY TRUCK DUMPER CHECKS | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002712 | WP-CHIPS TO SILOS & DIGESTER | HIN-010-040 | SILOS & CHIP THICKNESS SCREENING | WP | Wood Processing | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 194.00 / 388.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002632 | WP-CHIPS TO SILOS & DIGESTER | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002714 | WP-CTS BASIC CARE ALL FLOORS | HIN-010-040 | SILOS & CHIP THICKNESS SCREENING | WP | Wood Processing | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 65 | Ready to Execute | 0.00 / 776.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002634 | WP-CTS BASIC CARE ALL FLOORS | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002470 | CHGE SRV 083SRV15 THRD | HIN/083SRV15 | VALVE, SAFETY RELIEF, DE-ICEING BLOWE... | WTREAT | Water Treatment | 23.06.2025 | 23.06.2025 | PM_I_PF | Pipe Fitters | 26.05.2025 | IP1020250526 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 1,556.14 / 1,700.48 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002510 | CHGE SRV 083SRV15 THRD | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002680 | WT-STAVE LINE-30 | HIN-050-080-010-020 | LINE, STAVE PUMPHOUSE TO WATER TREATMENT | WTREAT | Water Treatment | 23.06.2025 | 23.06.2025 | PM_I_CA | Carpenter | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 970.00 / 1,115.50 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002600 | WT-STAVE LINE-30 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002682 | WTP TURBIDITY WEEKLY 83AI9258 | HIN/083Z9258 | FILTERED WATER TURBIDITY | WTREAT | Water Treatment | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 08.06.2025 | IP1020250608 |  | 1 | in operation | 91100016 | Mike Kerr | 65 | Ready to Execute | 0.00 / 194.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002602 | WTP TURBIDITY WEEKLY 83AI9258 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200002720 | WATER TREATMENT/EFFLUENT CLAIRIFIER | HIN-050-080 | WATER SYSTEMS | WTREAT | Water Treatment | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 08.06.2025 | IP1020250608 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 388.00 / 388.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002640 | WATER TREATMENT/EFFLUENT CLAIRIFIER | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200001959 | 3M OIL ANALYSIS ROUTE - FL | HIN-030-030-090 | CHEMICAL UNLOADING GENERAL | BLEACH | Bleach | 2025-06-02 | 2025-06-03 | PM_I_LM | Lube Mechanics | 2025-03-30 | IP1020250330 |  | 1 | in operation |  |  | 70 | Work Started | 0.00 / 1,940.00 / 970.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200001899 | 3M OIL ANALYSIS ROUTE - FL | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002441 | BLEACH & R8-LUBE-7 | HIN-030-010 | BLEACH PLANT | BLEACH | Bleach | 2025-06-02 | 2025-06-02 | PM_I_LM | Lube Mechanics | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 970.00 / 970.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002381 | BLEACH & R8-LUBE-7 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002462 | BLEACH & R8-LUBE-30 | HIN-030-010 | BLEACH PLANT | BLEACH | Bleach | 2025-06-02 | 2025-06-02 | PM_I_LM | Lube Mechanics | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 970.00 / 970.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002402 | BLEACH & R8-LUBE-30 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002367 | 1M - KAPPA | HIN/038Z1667 | KAPPA ANALYZER | BROWN | Brownstock | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2025-05-11 | IP1020250511 |  | 1 | in operation | 91100020 | Carl Redahl | 85 | TECO | 0.00 / 194.00 / 582.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002297 | 1M - KAPPA | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002442 | WEEKLY LUB IN BROWNSTOCK | HIN-020-020 | BROWN STOCK | BROWN | Brownstock | 2025-06-02 | 2025-06-02 | PM_I_LM | Lube Mechanics | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 970.00 / 970.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002382 | WEEKLY LUB IN BROWNSTOCK | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002446 | CLEANING OF WASHER SHOWERS 1A & 4B -1M | HIN-020-020 | BROWN STOCK | BROWN | Brownstock | 2025-06-02 | 2025-06-03 | PM_I_MW | Millwright | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 65 | Ready to Execute | 0.00 / 388.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002386 | CLEANING OF WASHER SHOWERS 1A & 4B -1M | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002456 | WEEKLY KAPPA | HIN/038Z1667 | KAPPA ANALYZER | BROWN | Brownstock | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2025-05-18 | IP1020250518 |  | 1 | in operation | 91100020 | Carl Redahl | 85 | TECO | 0.00 / 194.00 / 388.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002396 | WEEKLY KAPPA | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002106 | SRVC-GREASE & IV STRAIN GAUGES | HIN/034Z1260 | IMPREGNATION VESSEL CHIP LEVEL | DIGESTER | Digester | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2025-05-12 | IP1020250512 |  | 1 | in operation | 91100020 | Carl Redahl | 85 | TECO | 0.00 / 194.00 / 1,381.54 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002046 | SRVC-GREASE & IV STRAIN GAUGES | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002285 | PRESSURE SWITCH 034Z1355 | HIN/034Z1355 | SEAL WATER | DIGESTER | Digester | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2025-05-05 | IP1020250505 |  | 1 | in operation | 91100020 | Carl Redahl | 85 | TECO | 0.00 / 194.00 / 388.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002215 | PRESSURE SWITCH 034Z1355 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002289 | DIG-DEPT SAFETY CHECKS-30 | HIN-020 | DIGESTER / BROWN STOCK | DIGESTER | Digester | 2025-06-02 | 2025-06-02 | PM_I_MW | Millwright | 2025-05-05 | IP1020250505 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 194.00 / 194.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002219 | DIG-DEPT SAFETY CHECKS-30 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002435 | P-VIB-SOUTH-7 | HIN-020 | DIGESTER / BROWN STOCK | DIGESTER | Digester | 2025-06-02 | 2025-06-05 | PM_I_LM | Lube Mechanics | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 3,880.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002365 | P-VIB-SOUTH-7 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002459 | DIG- WEEKLY LUBE | HIN-020-010-120 | DIGESTER, GENERAL | DIGESTER | Digester | 2025-06-02 | 2025-06-03 | PM_I_LM | Lube Mechanics | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 1,940.00 / 1,940.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002399 | DIG- WEEKLY LUBE | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002484 | Weekly E/I South Shop Cleanup | HIN-100-030-090-020 | EI SHOPS - SOUTH (EIS) | DIGESTER | Digester | 2025-06-03 | 2025-06-03 | PM_I_EL | Electrical | 2025-05-20 | IP1020250520 |  | 1 | in operation | 91100020 | Carl Redahl | 70 | Work Started | 0.00 / 727.50 / 291.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002414 | Weekly E/I South Shop Cleanup | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-03
1200002432 | 7-JANITORIAL | HIN-090 | MOVERS AND SHAKERS | MOB | Mobile | 2025-06-02 | 2025-06-05 | PM_I_HDM | Heavy Duty Mechanics | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 80 | Work Done | 0.00 / 3,880.00 / 3,880.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002362 | 7-JANITORIAL | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002444 | WEEKLY STINGER OPERATION | HIN-090-020 | MOBILE EQUIPMENT | MOB | Mobile | 2025-06-02 | 2025-06-05 | PM_I_HDM | Heavy Duty Mechanics | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 3,880.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002384 | WEEKLY STINGER OPERATION | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002451 | WP-WEEKLY GARAGE SHOP CLEAN UP | HIN-100-040-030 | BUILDINGS, MILL GARAGE | MOB | Mobile | 2025-06-05 | 2025-06-05 | PM_I_HDM | Heavy Duty Mechanics | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 1,940.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002391 | WP-WEEKLY GARAGE SHOP CLEAN UP | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-05
1200002452 | GREASING UNIT & CHECK FOR DEFICIENCIES. | HIN/MOB056 | TRUCK, MILL WASTE DISPOSAL UNIT 381 | MOB | Mobile | 2025-06-03 | 2025-06-03 | PM_I_HDM | Heavy Duty Mechanics | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 194.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002392 | GREASING UNIT & CHECK FOR DEFICIENCIES. | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-03
1200002464 | COLLECT HOURS ON MOBILE EQUIP | HIN-100-040-020 | MAIN MILL GARAGE GENERAL | MOB | Mobile | 2025-06-02 | 2025-06-02 | PM_I_HDM | Heavy Duty Mechanics | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 194.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002404 | COLLECT HOURS ON MOBILE EQUIP | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200000440 | CHGE SRV 50SRV22 | HIN/050SRV22 | THERMAL RELIEF VALVE, TRIM SQUIRT SKI... | MR | Machine Room | 2025-06-02 | 2025-06-02 | PM_I_PF | Pipe Fitters | 2024-12-03 | IP1020241203 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 343.92 / 683.42 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200000420 | CHGE SRV 50SRV22 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002288 | MR-DEPT SAFETY CHECKS - 30 | HIN-060 | MACHINE ROOM | MR | Machine Room | 2025-06-02 | 2025-06-02 | PM_I_MW | Millwright | 2025-05-05 | IP1020250505 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 485.00 / 194.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002218 | MR-DEPT SAFETY CHECKS - 30 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002317 | DAY1, WEEK10,BALE LINE RELIABILITY | HIN-060-030-170 | BALE LINE B | MR | Machine Room | 2025-06-02 | 2025-06-02 | PM_I_MW | Millwright | 2025-05-04 | IP1020250504 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 97.00 / 97.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002237 | DAY1, WEEK10,BALE LINE RELIABILITY | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002318 | (WR) DAY2, WEEK10,BALE LINE RELIABILITY | HIN-060-030-170 | BALE LINE B | MR | Machine Room | 2025-06-02 | 2025-06-02 | PM_I_MW | Millwright | 2025-05-04 | IP1020250504 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 252.20 / 252.20 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002238 | (WR) DAY2, WEEK10,BALE LINE RELIABILITY | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002319 | DAY3, WEEK10,BALE LINE RELIABILITY | HIN-060-030-170 | BALE LINE B | MR | Machine Room | 2025-06-02 | 2025-06-02 | PM_I_MW | Millwright | 2025-05-04 | IP1020250504 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 97.00 / 97.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002239 | DAY3, WEEK10,BALE LINE RELIABILITY | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002320 | DAY4, WEEK10,BALE LINE RELIABILITY | HIN-060-030-170 | BALE LINE B | MR | Machine Room | 2025-06-02 | 2025-06-02 | PM_I_MW | Millwright | 2025-05-04 | IP1020250504 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 97.00 / 97.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002240 | DAY4, WEEK10,BALE LINE RELIABILITY | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002368 | SCANNER 1M - BRIGHTNESS & ODI CAL | HIN/050Z3656 | BASIS WEIGHT DRY END | MR | Machine Room | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2025-05-11 | IP1020250511 |  | 1 | in operation | 91100020 | Carl Redahl | 85 | TECO | 0.00 / 194.00 / 776.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002298 | SCANNER 1M - BRIGHTNESS & ODI CAL | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002397 | Turn rebuilt rolls in roll room | HIN-100-030-010-030 | MAIN SHOP GENERAL | MR | Machine Room | 2025-06-02 | 2025-06-02 | PM_I_MW | Millwright | 2025-05-11 | IP1020250511 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 194.00 / 194.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002327 | Turn rebuilt rolls in roll room | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002420 | HVAC CHECKS -M.I.S.-M-02 | HIN/00611711 | HAVC, I.T. SERVER ROOM | MR | Machine Room | 2025-06-05 | 2025-06-05 | PM_I_EL | Electrical | 2025-05-15 | IP1020250515 |  | 1 | in operation | 91100020 | Carl Redahl | 85 | TECO | 0.00 / 194.00 / 291.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002350 | HVAC CHECKS -M.I.S.-M-02 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-05
1200002437 | WEEKLY SCANNER CHECK & CLEANING | HIN/050Z3656 | BASIS WEIGHT DRY END | MR | Machine Room | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2025-05-18 | IP1020250518 |  | 1 | in operation | 91100020 | Carl Redahl | 85 | TECO | 0.00 / 194.00 / 388.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002367 | WEEKLY SCANNER CHECK & CLEANING | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002439 | MACHINE-LUBE-7 | HIN-060 | MACHINE ROOM | MR | Machine Room | 2025-06-02 | 2025-06-04 | PM_I_LM | Lube Mechanics | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 65 | Ready to Execute | 0.00 / 2,910.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002369 | MACHINE-LUBE-7 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002461 | WEEKLY ODI CLEANING & CAL | HIN/050Z3656 | BASIS WEIGHT DRY END | MR | Machine Room | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2025-05-18 | IP1020250518 |  | 1 | in operation | 91100020 | Carl Redahl | 85 | TECO | 0.00 / 174.60 / 582.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002401 | WEEKLY ODI CLEANING & CAL | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002466 | MR-CLEANERS & ROOF | HIN-060 | MACHINE ROOM | MR | Machine Room | 2025-06-02 | 2025-06-02 | PM_I_MW | Millwright | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 582.00 / 582.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002406 | MR-CLEANERS & ROOF | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002458 | PH-POWERHOUSE | HIN-050-060-020 | BOILER FEEDWATER SYSTEM | PH | Powerhouse | 2025-06-02 | 2025-06-02 | PM_I_MW | Millwright | 2025-05-18 | IP1020250518 |  | 1 | in operation | 91100108 | Mark Parker | 85 | TECO | 0.00 / 776.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002398 | PH-POWERHOUSE | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002440 | PULP WAREHOUSE-LUBE-7 | HIN-070 | PULP WAREHOUSE | PLPWRHSE | Pulp Warehouse | 2025-06-02 | 2025-06-02 | PM_I_LM | Lube Mechanics | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 65 | Ready to Execute | 0.00 / 970.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002380 | PULP WAREHOUSE-LUBE-7 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002465 | EL_UNITYER PRINTERS_WEEKLY RR | HIN/071217 | PRINTERS, UNITYER NORTH ARM, A-LINE | PLPWRHSE | Pulp Warehouse | 2025-06-02 | 2025-06-02 | PM_I_EL | Electrical | 2025-05-18 | IP1020250518 |  | 1 | in operation | 91100020 | Carl Redahl | 80 | Work Done | 0.00 / 97.00 / 156.06 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002405 | EL_UNITYER PRINTERS_WEEKLY RR | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002443 | PR- WKLY LUB IN P&R | HIN-050-020 | RECOVERY BOILER SYSTEMS | PRECIPS | Precips | 2025-06-02 | 2025-06-05 | PM_I_LM | Lube Mechanics | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 3,880.00 / 3,100.90 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002383 | PR- WKLY LUB IN P&R | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002463 | PR- 1M - LUBE IN POWER & RECOVERY | HIN-050-020 | RECOVERY BOILER SYSTEMS | PRECIPS | Precips | 2025-06-02 | 2025-06-05 | PM_I_LM | Lube Mechanics | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 3,880.00 / 2,910.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002403 | PR- 1M - LUBE IN POWER & RECOVERY | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002113 | COND-INDICAT-#3 RB CONDENSATE | HIN/056Z7991 | RB #3 CONDENSATE CONDUCTIVITY INDICATION | PRWBOILER | Power Boilers | 2025-06-05 | 2025-06-05 | PM_I_IN | Instrumentation | 2025-05-17 | IP1020250517 |  | 1 | in operation | 91100016 | Mike Kerr | 65 | Ready to Execute | 0.00 / 194.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002373 | COND-INDICAT-#3 RB CONDENSATE | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-05
1200002394 | PR-TRV_GRATE-W | HIN-050-040-040-070 | GRATES, TRAVELING # 3 POWER BOILER | PRWBOILER | Power Boilers | 2025-06-02 | 2025-06-02 | PM_I_MW | Millwright | 2025-05-11 | IP1020250511 |  | 1 | in operation | 91100108 | Mark Parker | 65 | Ready to Execute | 0.00 / 194.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002324 | PR-TRV_GRATE-W | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002404 | Weekly E/I North Shop Cleanup | HIN-100-030-090-010 | EI SHOPS - NORTH (EIN) | PRWBOILER | Power Boilers | 2025-06-05 | 2025-06-05 | PM_I_EL | Electrical | 2025-05-22 | IP1020250522 |  | 1 | in operation | 91100016 | Mike Kerr | 70 | Work Started | 0.00 / 727.50 / 734.74 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002344 | Weekly E/I North Shop Cleanup | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-05
1200002427 | CONDUCT-INDICAT-OUTLET ANION UNIT B | HIN/056Z7910 | ANION B CONDUCTIVITY INDICATION AND I... | PRWBOILER | Power Boilers | 2025-06-06 | 2025-06-06 | PM_I_IN | Instrumentation | 2025-05-16 | IP1020250516 |  | 1 | in operation | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 194.00 / 388.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002357 | CONDUCT-INDICAT-OUTLET ANION UNIT B | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-06
1200002438 | RECAUST LUBE WEEKLY | HIN-040-010 | RECAUST SYSTEMS | RECAUST | Recaust | 2025-06-02 | 2025-06-04 | PM_I_LM | Lube Mechanics | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 2,910.00 / 4,989.99 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002368 | RECAUST LUBE WEEKLY | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002107 | UNIT - VAP ABSORB-RB3 RACK & MCC ROOM | HIN/05228711 | UNIT - VAPOR ABSORBER 52287 - RB3 RAC... | RECBOILER | Recovery Boilers | 2025-06-02 | 2025-06-02 | PM_I_EL | Electrical | 2025-05-12 | IP1020250512 |  | 1 | in operation | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 203.68 / 194.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002047 | UNIT - VAP ABSORB-RB3 RACK & MCC ROOM | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002430 | A/B-CONDUCT-INDICAT-RB3 CONDEN DMP STN | HIN/056Z4598 | #3 RB CONDENSATE CONDUCTIVITY DUMP ST... | RECBOILER | Recovery Boilers | 2025-06-06 | 2025-06-06 | PM_I_IN | Instrumentation | 2025-05-16 | IP1020250516 |  | 1 | in operation | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 194.00 / 388.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002360 | A/B-CONDUCT-INDICAT-RB3 CONDEN DMP STN | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-06
1200002436 | P-VIB-NORTH-7 | HIN-050 | POWER AND RECOVERY | RECBOILER | Recovery Boilers | 2025-06-02 | 2025-06-05 | PM_I_LM | Lube Mechanics | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 65 | Ready to Execute | 0.00 / 3,880.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002366 | P-VIB-NORTH-7 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002460 | PB3 8TH FLR RECIRC & VENT FAN FILTRS | HIN/059221 | HVAC - RECIRCULATION & VENTILATION FAN | RECBOILER | Recovery Boilers | 2025-06-02 | 2025-06-02 | PM_I_EL | Electrical | 2025-05-18 | IP1020250518 |  | 1 | in operation | 91100016 | Mike Kerr | 80 | Work Done | 0.00 / 388.00 / 291.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002400 | PB3 8TH FLR RECIRC & VENT FAN FILTRS | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002431 | HVAC CHECKS-LAB / TECH-W-2 | HIN/07010511 | AIR CONDITIONING, CONST HUMIDITY LAB | TECHNICAL | Technical | 2025-06-02 | 2025-06-02 | PM_I_EL | Electrical | 2025-05-18 | IP1020250518 |  | 1 | in operation | 91100020 | Carl Redahl | 85 | TECO | 0.00 / 97.00 / 601.24 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002361 | HVAC CHECKS-LAB / TECH-W-2 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002387 | HVAC VAPOR ABSORBER 57138 - TG1 MCC RM | HIN/05713811 | VAPOR ABSORBER 57138 - TG1 MCC RM | TURBINES | Turbines | 2025-06-02 | 2025-06-02 | PM_I_EL | Electrical | 2025-05-11 | IP1020250511 |  | 1 | in operation | 91100016 | Mike Kerr | 80 | Work Done | 0.00 / 376.49 / 242.50 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002317 | HVAC VAPOR ABSORBER 57138 - TG1 MCC RM | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002428 | CONDUCT-INDICAT-COND FROM FL-DUMP STN | HIN/056Z4599 | PULPING/DIGESTER CONDENSATE CONDUCTIV... | TURBINES | Turbines | 2025-06-06 | 2025-06-06 | PM_I_IN | Instrumentation | 2025-05-16 | IP1020250516 |  | 1 | in operation | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 194.00 / 388.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002358 | CONDUCT-INDICAT-COND FROM FL-DUMP STN | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-06
1200002429 | A/B-CONDUCT-INDICAT-TG1 CONDEN DMP STN | HIN/056Z4579 | #1 TG CONDENSER CONDENSATE CONDUCTIVI... | TURBINES | Turbines | 2025-06-06 | 2025-06-06 | PM_I_IN | Instrumentation | 2025-05-16 | IP1020250516 |  | 1 | in operation | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 194.00 / 388.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002359 | A/B-CONDUCT-INDICAT-TG1 CONDEN DMP STN | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-06
1200002119 | BCPM TOWER THREE | HIN/021117 | Tower #3 | WP | Wood Processing | 2025-06-02 | 2025-06-02 | PM_I_MW | Millwright | 2025-05-19 | IP1020250519 |  | 1 | in operation | 91100108 | Mark Parker | 85 | TECO | 0.00 / 388.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002379 | BCPM TOWER THREE | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002433 | FSS-LUBE 1M | HIN-010-040 | SILOS & CHIP THICKNESS SCREENING | WP | Wood Processing | 2025-06-02 | 2025-06-03 | PM_I_LM | Lube Mechanics | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 1,455.00 / 1,455.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002363 | FSS-LUBE 1M | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002434 | FSS-LUBE WEEKLY | HIN-010-040-010 | SILO STORAGE AND CONVEYING | WP | Wood Processing | 2025-06-02 | 2025-06-04 | PM_I_LM | Lube Mechanics | 2025-05-18 | IP1020250518 |  | 1 | in operation |  |  | 85 | TECO | 0.00 / 2,425.00 / 2,425.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002364 | FSS-LUBE WEEKLY | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002457 | ELEC- WEEKLY TRUCK DUMPER CHECKS | HIN/02212204 | CIRCUIT CNTL, MAIN DUMPER DISCHARGE | WP | Wood Processing | 2025-06-02 | 2025-06-02 | PM_I_EL | Electrical | 2025-05-18 | IP1020250518 |  | 1 | in operation | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 194.00 / 194.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002397 | ELEC- WEEKLY TRUCK DUMPER CHECKS | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002467 | WP-RECLAIMS & CHIP DUMPERS | HIN-010-050 | PURCHASE CHIPS | WP | Wood Processing | 2025-06-02 | 2025-06-02 | PM_I_MW | Millwright | 2025-05-18 | IP1020250518 |  | 1 | in operation | 91100108 | Mark Parker | 85 | TECO | 0.00 / 776.00 / 0.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002407 | WP-RECLAIMS & CHIP DUMPERS | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200002445 | WTP TURBIDITY WEEKLY 83AI9258 | HIN/083Z9258 | FILTERED WATER TURBIDITY | WTREAT | Water Treatment | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2025-05-18 | IP1020250518 |  | 1 | in operation | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 194.00 / 194.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200002385 | WTP TURBIDITY WEEKLY 83AI9258 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100005829 | the doctor board is chipped | HIN/063Z7384 | LIME MUD PRECOAT FILTER DOCTOR BLADE ... | KILN | Lime Kiln | 27.06.2025 | 27.06.2025 | PM_I_MW | Millwright | 27.06.2025 | RICHARBR | [5 empty] | 65 | Ready to Execute | 0.00 / 0.00 / 1,157.56 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006296 | the doctor board is chipped | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 27.06.2025
1100005770 | Shear Pin has broke | HIN/05912103 | MOTOR, GRATE DISCHARGE ASH CONVEYOR | PRWBOILER | Power Boilers | 26.06.2025 | 26.06.2025 | PM_I_MW | Millwright | 26.06.2025 | RICHARBR | [5 empty] | 80 | Work Done | 0.00 / 0.00 / 194.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006243 | Shear Pin has broke | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 26.06.2025
1100005771 | Valve is plugged | HIN/059M127 | BOILER VISCODYNE ROTARY VALVE | PRWBOILER | Power Boilers | 26.06.2025 | 26.06.2025 | PM_I_MW | Millwright | 26.06.2025 | RICHARBR | [5 empty] | 80 | Work Done | 0.00 / 0.00 / 145.50 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006244 | Valve is plugged | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 26.06.2025
1100005772 | Valve is plugged | HIN/059M128 | BOILER VISCODYNE ROTARY VALVE | PRWBOILER | Power Boilers | 26.06.2025 | 26.06.2025 | PM_I_MW | Millwright | 26.06.2025 | RICHARBR | [5 empty] | 80 | Work Done | 0.00 / 0.00 / 145.50 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006245 | Valve is plugged | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 26.06.2025
1200000005 | BMS PB- VERIFY PRESSURE XMITTR Z4248 | HIN/059Z4248 | FD FAN INLET PRESSURE INDICATION_BMS-... | PRWBOILER | Power Boilers | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 20.11.2024 | IP1020241120 |  | 8 | Next Planned Shut | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 621.50 / 194.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200000005 | BMS PB- VERIFY PRESSURE XMITTR Z4248 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200000010 | BMS PB3-DRUM LEVEL SWITCHES-INSPT/TST | HIN/059Z4006 | MAGTECH DRUM LEVEL SWITCHES_SOUTH_BMS... | PRWBOILER | Power Boilers | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 20.11.2024 | IP1020241120 |  | 8 | Next Planned Shut | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 621.50 / 388.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200000010 | BMS PB3-DRUM LEVEL SWITCHES-INSPT/TST | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200000011 | BMS PB- VERIFY IGNITOR GAS FLOW TX Z4153 | HIN/059Z4153 | PILOT GAS FLOW INDICATION_BMS-SCE- | PRWBOILER | Power Boilers | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 20.11.2024 | IP1020241120 |  | 8 | Next Planned Shut | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 524.50 / 194.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200000011 | BMS PB- VERIFY IGNITOR GAS FLOW TX Z4153 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200000012 | BMS VERIFY DRUM LEVEL XMITTR Z4007 | HIN/059Z4007 | DRUM LEVEL CONTROL_BMS-SCE- | PRWBOILER | Power Boilers | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 20.11.2024 | IP1020241120 |  | 8 | Next Planned Shut | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 524.50 / 194.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200000012 | BMS VERIFY DRUM LEVEL XMITTR Z4007 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1200000016 | BMS PB-VERIFY FEEDWATER CNTL | HIN/059Z4001 | FEED WATER FLOW CONTROL_BMS-SCE | PRWBOILER | Power Boilers | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 20.11.2024 | IP1020241120 |  | 8 | Next Planned Shut | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 2,001.00 / 582.00 CAD | 3 | Technically Completed | YA02 | Proactive Maintenance | 9200000016 | BMS PB-VERIFY FEEDWATER CNTL | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100005759 | IK 31 repacking | HIN/052132 | SOOTBLOWER, #31 | RECBOILER | Recovery Boilers | 27.06.2025 | 27.06.2025 | PM_I_MW | Millwright | 27.06.2025 | RICHARBR | [5 empty] | 85 | TECO | 0.00 / 0.00 / 630.50 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006235 | IK 31 repacking | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 27.06.2025
1100005761 | Potential Fuse replacement | HIN/066Z4800 | REGULATOR - TRANSFER AUTO TO MANUAL | TURBINES | Turbines | 23.06.2025 | 23.06.2025 | PM_I_EL | Electrical | 22.06.2025 | RICHARBR | [5 empty] | 65 | Ready to Execute | 0.00 / 0.00 / 4,587.84 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006203 | Potential Fuse replacement | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 23.06.2025
1200000204 | LIQUOR-PURGE-LEVEL-CNTL-EV3 EFFECT 1 | HIN/051Z6301 | #1 EFFECT LEVEL CONTROL | EVAPS | Evaps/Recovery | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2024-11-20 | IP1020241120 |  | 8 | Next Planned Shut | 91100016 | Mike Kerr | 80 | Work Done | 0.00 / 194.00 / 194.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200000204 | LIQUOR-PURGE-LEVEL-CNTL-EV3 EFFECT 1 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200001767 | EV3 - PURGE-LEVEL-CNTL-EV3 EFFECT 4 | HIN/051Z6304 | #4 EFFECT LEVEL CONTROL | EVAPS | Evaps/Recovery | 2025-06-04 | 2025-06-04 | PM_I_IN | Instrumentation | 2025-03-16 | IP1020250316 |  | 8 | Next Planned Shut | 91100016 | Mike Kerr | 80 | Work Done | 0.00 / 194.00 / 194.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200001717 | EV3 - PURGE-LEVEL-CNTL-EV3 EFFECT 4 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-04
1200001769 | LIQUOR-PURGE-LEVEL-CNTL-EVAPS 3 EFFECT 2 | HIN/051Z6302 | #2 EFFECT LEVEL CONTROL | EVAPS | Evaps/Recovery | 2025-06-04 | 2025-06-04 | PM_I_IN | Instrumentation | 2025-03-16 | IP1020250316 |  | 8 | Next Planned Shut | 91100016 | Mike Kerr | 80 | Work Done | 0.00 / 194.00 / 194.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200001719 | LIQUOR-PURGE-LEVEL-CNTL-EVAPS 3 EFFECT 2 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-04
1200001770 | PURGE-LEVEL-CNTL - #3 EVAPS #3 EFFECT | HIN/051Z6303 | #3 EFFECT LEVEL CONTROL | EVAPS | Evaps/Recovery | 2025-06-04 | 2025-06-04 | PM_I_IN | Instrumentation | 2025-03-16 | IP1020250316 |  | 8 | Next Planned Shut | 91100016 | Mike Kerr | 80 | Work Done | 0.00 / 194.00 / 194.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200001720 | PURGE-LEVEL-CNTL - #3 EVAPS #3 EFFECT | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-04
1200000951 | VIDEO - INDICATION - PB3 BED CAMERA | HIN/059Z4190 | BED BUG CAMERA | PRWBOILER | Power Boilers | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2025-01-31 | IP1020250131 |  | 8 | Next Planned Shut | 91100016 | Mike Kerr | 80 | Work Done | 0.00 / 8,228.27 / 194.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200001041 | VIDEO - INDICATION - PB3 BED CAMERA | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200000952 | PB3 STEAM-FLOW-INDICAT-SOOTBLOWING STEAM | HIN/059Z4019 | SOOTBLOWING STEAM FLOW INDICATION | PRWBOILER | Power Boilers | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2025-01-31 | IP1020250131 |  | 8 | Next Planned Shut | 91100016 | Mike Kerr | 80 | Work Done | 0.00 / 194.00 / 194.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200001042 | PB3 STEAM-FLOW-INDICAT-SOOTBLOWING STEAM | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200001688 | WEIGHT-INDICAT-PB3 HOG OVRFLW TO RECLAIM | HIN/059Z4067 | HOG OVERFLOW TO RECLAIM (59-218) FLOW... | PRWBOILER | Power Boilers | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2025-03-13 | IP1020250313 |  | 8 | Next Planned Shut | 91100016 | Mike Kerr | 80 | Work Done | 0.00 / 194.00 / 194.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200001638 | WEIGHT-INDICAT-PB3 HOG OVRFLW TO RECLAIM | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1200001804 | WEIGHT-CNTL-WEIGHTOMETER (CONV 59-215) | HIN/059Z4066 | HOG TO FEEDERS (59-215) FLOW CONTROL | PRWBOILER | Power Boilers | 2025-06-05 | 2025-06-05 | PM_I_IN | Instrumentation | 2025-03-20 | IP1020250320 |  | 8 | Next Planned Shut | 91100079 | Michelle Stiller | 65 | Ready to Execute | 0.00 / 388.00 / 0.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200001744 | WEIGHT-CNTL-WEIGHTOMETER (CONV 59-215) | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-05
1100005298 | level is not reading consistent | HIN/061Z7522 | #4 CAUSTICIZER LEVEL CONTROL | RECAUST | Recaust | 2025-06-05 | 2025-06-05 | PM_I_IN | Instrumentation | 2025-06-05 | RICHARBR | [5 empty] | 85 | TECO | 0.00 / 0.00 / 97.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005829 | level is not reading consistent | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-05
1200002132 | LEVEL-CNTL-LIME MUD PUMPING TANK (LMPT) | HIN/061Z7570 | LIME MUD PUMP TANK LEVEL CONTROL | RECAUST | Recaust | 2025-06-03 | 2025-06-03 | PM_I_IN | Instrumentation | 2025-05-13 | IP1020250513 |  | 8 | Next Planned Shut | 91100016 | Mike Kerr | 80 | Work Done | 0.00 / 194.00 / 194.00 CAD | 2 | Released | YA02 | Proactive Maintenance | 9200002332 | LEVEL-CNTL-LIME MUD PUMPING TANK (LMPT) | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-03
1100005299 | pond sampler is reading wrong | HIN/087Z9166 | POND INLET SAMPLER | WEFFLUE | Water Effluent | 2025-06-05 | 2025-06-05 | PM_I_IN | Instrumentation | 2025-06-05 | RICHARBR | [5 empty] | 85 | TECO | 0.00 / 0.00 / 194.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005850 | pond sampler is reading wrong | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-05
1100005226 | WMATL - Replace pulleys | HIN-100-050-060-050 | HVAC | BROWN | Brownstock | 23.06.2025 | 23.06.2025 | PM_I_HVA | Heating Ventilation Air Condition | 27.05.2025 | TESTON | Neil Testo | 1 | in operation | 91100137 | Christina Chanthapanya | 65 | Ready to Execute | 0.00 / 738.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005535 | Replace pulleys | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100005282 | Brownstock Elevator Not Communicating | HIN/03811411 | ELEVATOR, FREIGHT BROWNSTOCK | BROWN | Brownstock | 25.06.2025 | 25.06.2025 | PM_E_EL | External - Electrician | 29.05.2025 | ZYGMUNTB | Bryan Zygmunt |  |  | 91100119 | Bryan Zygmunt | 85 | TECO | 0.00 / 0.00 / 0.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005703 | Brownstock Elevator Not Communicating | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 25.06.2025
1100005751 | Replace 1A washer wire | HIN/03821912 | WASHER, DRUM # 1 A | BROWN | Brownstock | 24.06.2025 | 25.06.2025 | PM_I_MW | Millwright | 24.06.2025 | HORMANNK | Kevin Hormann |  |  | 91100103 | Derek Goshulak | 65 | Ready to Execute | 0.00 / 22,770.00 / 3,649.46 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006232 | Replace 1A washer wire | 1 | Immediately < 24h |  | Standard Order | WK 26-2025 | 24.06.2025
1100005794 | 38-401 | HIN/038401 | A/C UNIT ELEC ROOM | BROWN | Brownstock | 25.06.2025 | 26.06.2025 | PM_I_HVA | Heating Ventilation Air Condition | 25.06.2025 | TESTON | Neil Testo | 1 | in operation | 91100137 | Christina Chanthapanya | 85 | TECO | 0.00 / 1,940.00 / 0.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006138 | 38-401 | 2 | Rectify < 48 h |  | Standard Order | WK 26-2025 | 25.06.2025
1100001146 | Rebuild 34-156 Bingham pump | HIN/03415601 | PUMP, WHITE LIQUOR # 1 | DIGESTER | Digester | 23.06.2025 | 27.06.2025 | PM_I_RB | Rebuild Shop | 31.12.2024 | TESTON | Neil Testo | 0 | not in operation | 91100117 | Veronica Whitford | 70 | Work Started | 0.00 / 14,040.60 / 8,442.86 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100001336 | Rebuild 34-156 pump | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100004911 | REPLACE NUCLEAR SIGNS IN THE FIELD | HIN-100-030-090-020 | EI SHOPS - SOUTH (EIS) | DIGESTER | Digester | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 15.05.2025 | TESTON | Neil Testo | 1 | in operation | 91100016 | Mike Kerr | 65 | Ready to Execute | 0.00 / 1,438.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005335 | REPLACE NUCLEAR SIGNS IN THE FIELD | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100000205 | (CWB) REPLACE BOTTOM 6" OF LADDER | HIN-050-010-020-210-020-020 | PLATFORMS, GRATING STAIRWAYS | EVAPS | Evaps/Recovery | 23.06.2025 | 25.06.2025 | PM_I_WE | Welders | 26.11.2024 | PALMERT | Tyler Palmer | 0 | not in operation | 91100176 | Jfletcher Orringe | 85 | TECO | 0.00 / 3,205.59 / 0.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100000237 | CWB - REPLACE WHOLE LADDER | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100004699 | Rebuild 51-103 pump | HIN/05110301 | PUMP, HEAVY BLACK LIQUOR PRODUCT | EVAPS | Evaps/Recovery | 23.06.2025 | 26.06.2025 | PM_I_RB | Rebuild Shop | 06.05.2025 | PALMERT | Tyler Palmer |  |  | 91100117 | Veronica Whitford | 65 | Ready to Execute | 0.00 / 9,362.68 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005111 | Rebuild 51-103 pump | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100004741 | WMTRL - REPLACE HORN AND STROBE | HIN/051Z6496A | H2S - #3 EVAPS HOTWELL AREA GROUND FLOOR | EVAPS | Evaps/Recovery | 27.06.2025 | 27.06.2025 | PM_I_EL | Electrical | 30.04.2025 | BLEACKLJ | Josh Bleackley | 1 | in operation | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 10,547.86 / 2,581.15 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005076 | REPLACE HORN AND STROBE | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 27.06.2025
1100005827 | Repair 70% piping, RB3 2nd flr | HIN-050-010-020-210-030-060 | PIPING, LIQUOR | EVAPS | Evaps/Recovery | 27.06.2025 | 04.07.2025 | PM_I_PF | Pipe Fitters | 27.06.2025 | OPSTEENJ | Johan Opsteen | 0 | not in operation | 91100009 | James Descheneau | 70 | Work Started | 0.00 / 15,554.28 / 2,468.90 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006294 | Repair 70% piping, RB3 2nd flr | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 27.06.2025
1100003669 | Replace circ fan 50-392 | HIN/05039206 | FAN, #75 DRYER CIRC FAN | MR | Machine Room | 24.06.2025 | 18.07.2025 | PM_E_MW | External - Millwright | 27.03.2025 | DIRCKSC | Caleb Dircks | 1 | in operation | 91100146 | Caleb Dircks | 65 | Ready to Execute | 0.00 / 25,205.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100003981 | Replace circ fan 50-392 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 24.06.2025
1100004510 | WMATL - lighting on PM1 side 2nd floor | HIN-060-020-040-100-010 | LIGHTING, ELECTRICAL SERVICES - PM1 G... | MR | Machine Room | 24.06.2025 | 27.06.2025 | PM_I_EL | Electrical | 22.04.2025 | CORRIGAJ | John Corrigan | 1 | in operation | 91100137 | Christina Chanthapanya | 65 | Ready to Execute | 0.00 / 27,690.82 / 11,495.23 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100004816 | Repair lighting on PM1 side 2nd floor | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 24.06.2025
1100004811 | Install Pressure Gauge on Gas Line | HIN-060-030-220-060-080 | PIPING, NATURAL GAS | MR | Machine Room | 23.06.2025 | 23.06.2025 | PM_I_PF | Pipe Fitters | 06.05.2025 | DIRCKSC | Caleb Dircks | 1 | in operation | 91100020 | Carl Redahl | 70 | Work Started | 0.00 / 403.66 / 194.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005181 | Install Pressure Gauge on Gas Line | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100005157 | Install additional lighting on A-line | HIN-060-020-040-100-010 | LIGHTING, ELECTRICAL SERVICES - PM1 G... | MR | Machine Room | 23.06.2025 | 23.06.2025 | PM_I_EL | Electrical | 28.05.2025 | DIRCKSC | Caleb Dircks | 1 | in operation | 91100020 | Carl Redahl | 85 | TECO | 0.00 / 3,000.38 / 4,756.99 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005672 | Install additional lighting on A-line | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100005279 | Adjust High High Limit Switch | HIN/049177 | CRANE, BRIDGE | MR | Machine Room | 25.06.2025 | 25.06.2025 | PM_E_EL | External - Electrician | 03.06.2025 | ZYGMUNTB | Bryan Zygmunt |  |  | 91100119 | Bryan Zygmunt | 85 | TECO | 0.00 / 0.00 / 0.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005788 | Adjust High High Limit Switch | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 25.06.2025
1100005529 | Structural Engineer Inspection | HIN/049177 | CRANE, BRIDGE | MR | Machine Room | 25.06.2025 | 25.06.2025 | PM_E_NDT | External - Non-Destructive Test | 11.06.2025 | ZYGMUNTB | Bryan Zygmunt |  |  | 91100119 | Bryan Zygmunt | 85 | TECO | 0.00 / 0.00 / 0.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005994 | Structural Engineer Inspection | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 25.06.2025
1100005726 | 88106 Main Lab | HIN/08810603 | MOTOR, PRODUCTION OFFICES UNIT 1 | MR | Machine Room | 23.06.2025 | 23.06.2025 | PM_I_HVA | Heating Ventilation Air Condition | 18.06.2025 | DIRCKSC | Caleb Dircks | 1 | in operation | 91100020 | Carl Redahl | 65 | Ready to Execute | 0.00 / 1,940.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006116 | 88106 Main Lab | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100005727 | 88103 Crystal palace HVAC | HIN/088103 | CRYSTAL PALACE RETURN FAN, AIR HANDLI... | MR | Machine Room | 23.06.2025 | 23.06.2025 | PM_I_HVA | Heating Ventilation Air Condition | 18.06.2025 | DIRCKSC | Caleb Dircks | 1 | in operation | 91100020 | Carl Redahl | 65 | Ready to Execute | 0.00 / 970.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006117 | 88103 Crystal palace HVAC | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100005796 | Calibrate scanner to manual tests | HIN/050Z3661 | PULP BRIGHTNESS SCANNER | MR | Machine Room | 26.06.2025 | 26.06.2025 | PM_I_IN | Instrumentation | 26.06.2025 | DIRCKSC | Caleb Dircks |  |  | 91100020 | Carl Redahl | 80 | Work Done | 0.00 / 582.00 / 582.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006286 | Calibrate scanner to manual tests | 1 | Immediately < 24h |  | Standard Order | WK 26-2025 | 26.06.2025
1100005736 | High temp damper probe failures | HIN-050-020-010-110 | #3 RECOVERY PRECIPITATORS | PRECIPS | Precips | 23.06.2025 | 24.06.2025 | PM_I_IN | Instrumentation | 19.06.2025 | FRATTINK | Kim Frattinger | 1 | in operation | 91100079 | Michelle Stiller | 65 | Ready to Execute | 0.00 / 1,164.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006109 | High temp damper probe failures | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100004996 | Change lubricant to Mobilgear 600 XP 220 | HIN/05921402 | REDUCER, CONVEYOR HOG FUEL | PRWBOILER | Power Boilers | 23.06.2025 | 23.06.2025 | PM_I_LM | Lube Mechanics | 15.05.2025 | KILBREAG | Gord Kilbreath | 8 | Next Planned Shut | 91100117 | Veronica Whitford | 85 | TECO | 0.00 / 194.00 / 194.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005403 | Change lubricant to Mobilgear 600 XP 220 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100005725 | Positioner Alignment PB3 BFW | HIN/059Z4001 | FEED WATER FLOW CONTROL_BMS-SCE | PRWBOILER | Power Boilers | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 18.06.2025 | FRATTINK | Kim Frattinger | 1 | in operation | 91100079 | Michelle Stiller | 85 | TECO | 0.00 / 388.00 / 840.06 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006063 | Positioner Alignment PB3 BFW | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100005153 | Repair Screw RPM for Slaker Lime Feed | HIN/061Z7496 | #2 SLAKER HOT LIME SCREW SPEED CONTROL | RECAUST | Recaust | 23.06.2025 | 23.06.2025 | PM_I_EL | Electrical | 27.05.2025 | PALMERT | Tyler Palmer | 8 | Next Planned Shut | 91100137 | Christina Chanthapanya | 65 | Ready to Execute | 0.00 / 612.32 / 1,457.85 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005618 | Repair Screw RPM for Slaker Lime Feed | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100005804 | Packing has come apart 61-301 | HIN/06130101 | PUMP, # 2 CAUSTICIZER LIQ TO WLPF | RECAUST | Recaust | 25.06.2025 | 25.06.2025 | PM_I_MW | Millwright | 24.06.2025 | BLEACKLJ | Josh Bleackley | 0 | not in operation | 91100018 | Tyler Palmer | 85 | TECO | 0.00 / 3,595.67 / 1,940.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006127 | Packing has come apart 61-301 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 25.06.2025
1100001803 | TA25 N70% HBL heating coil outlet pipe | HIN-050-020-010-150-030-090 | PIPING, STEAM 80# | RECBOILER | Recovery Boilers | 23.06.2025 | 16.09.2025 | PM_I_PF | Pipe Fitters | 23.01.2025 | FRATTINK | Kim Frattinger | 9 | Annual Shut | 91100107 | Darryl Nichol | 70 | Work Started | 0.00 / 6,972.54 / 4,195.98 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100001971 | rpr N70% HBL heating coil outlet pipe | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100003591 | TA25 rpr desup cond drain pip (1st flr) | HIN-050-020-010-150-030-040 | PIPING, CONDENSATE | RECBOILER | Recovery Boilers | 23.06.2025 | 16.09.2025 | PM_I_PF | Pipe Fitters | 24.03.2025 | FRATTINK | Kim Frattinger | 9 | Annual Shut | 91100107 | Darryl Nichol | 70 | Work Started | 0.00 / 6,863.14 / 4,202.31 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100003888 | TA25 rpr desup cond drain pip (1st flr) | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100004630 | RB3 IK4 replace poppet valve | HIN/05210511 | SOOTBLOWER, #4 | RECBOILER | Recovery Boilers | 24.06.2025 | 24.06.2025 | PM_I_PF | Pipe Fitters | 29.04.2025 | FRATTINK | Kim Frattinger | 1 | in operation | 91100108 | Mark Parker | 85 | TECO | 0.00 / 1,378.74 / 2,422.01 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005017 | RB3 IK4 replace poppet valve | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 24.06.2025
1100004632 | RB3 IK17 replace poppet valve | HIN/05211811 | SOOTBLOWER, #17 | RECBOILER | Recovery Boilers | 24.06.2025 | 24.06.2025 | PM_I_PF | Pipe Fitters | 29.04.2025 | FRATTINK | Kim Frattinger | 1 | in operation | 91100108 | Mark Parker | 85 | TECO | 0.00 / 1,378.74 / 2,423.44 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005019 | RB3 IK17 replace poppet valve | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 24.06.2025
1100004761 | Replace condensate piping | HIN-050-020-010-150-030-040 | PIPING, CONDENSATE | RECBOILER | Recovery Boilers | 25.06.2025 | 23.07.2025 | PM_I_PF | Pipe Fitters | 01.05.2025 | MACKAYL | Launy MacKay | 1 | in operation | 91100107 | Darryl Nichol | 70 | Work Started | 0.00 / 15,834.34 / 4,360.51 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005121 | Replace condensate piping | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 25.06.2025
1100005257 | Replace sewer grating | HIN-050-020-010-150-020 | BUILDINGS, #3 RECOVERY | RECBOILER | Recovery Boilers | 24.06.2025 | 24.06.2025 | PM_I_WE | Welders | 28.05.2025 | KILBREAG | Gord Kilbreath | 1 | in operation | 91100049 | Gilles Grenier | 65 | Ready to Execute | 0.00 / 1,900.00 / 97.96 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005655 | Remove tripping hazard | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 24.06.2025
1100005276 | Clean plugged burner | HIN/05224611 | BURNER, # 3 LOAD CARRYING | RECBOILER | Recovery Boilers | 24.06.2025 | 24.06.2025 | PM_I_PF | Pipe Fitters | 30.05.2025 | KILBREAG | Gord Kilbreath | 1 | in operation | 91100059 | Gord Kilbreath | 85 | TECO | 0.00 / 980.42 / 106.10 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005741 | Clean plugged burner | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 24.06.2025
1100005277 | Clean plugged burner | HIN/05224711 | BURNER, # 4 LOAD CARRYING | RECBOILER | Recovery Boilers | 24.06.2025 | 24.06.2025 | PM_I_PF | Pipe Fitters | 30.05.2025 | KILBREAG | Gord Kilbreath | 1 | in operation | 91100059 | Gord Kilbreath | 85 | TECO | 0.00 / 980.42 / 106.10 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005742 | Clean plugged burner | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 24.06.2025
1100005284 | RB3 IK17 inspect track and canopy | HIN/05211811 | SOOTBLOWER, #17 | RECBOILER | Recovery Boilers | 24.06.2025 | 24.06.2025 | PM_I_MW | Millwright | 29.05.2025 | KILBREAG | Gord Kilbreath | 1 | in operation | 91100108 | Mark Parker | 85 | TECO | 0.00 / 10,542.33 / 11,801.88 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005713 | RB3 IK17 inspect track and canopy | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 24.06.2025
1100005288 | Drawing for Wo 1100001889 | HIN-050-020-010-150-030-110 | PIPING, STEAM 600# | RECBOILER | Recovery Boilers | 24.06.2025 | 24.06.2025 | PM_I_PF | Pipe Fitters | 30.05.2025 | FRATTINK | Kim Frattinger | 1 | in operation | 91100108 | Mark Parker | 65 | Ready to Execute | 0.00 / 485.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005708 | Drawing for Wo 1100001889 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 24.06.2025
1100005344 | Replace utility station air fittings | HIN-050-020-010-150-030-060 | PIPING, COMPRESSED AIR | RECBOILER | Recovery Boilers | 24.06.2025 | 26.06.2025 | PM_I_PF | Pipe Fitters | 03.06.2025 | KILBREAG | Gord Kilbreath | 1 | in operation | 91100059 | Gord Kilbreath | 85 | TECO | 0.00 / 2,320.80 / 1,451.56 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005801 | Replace utility station air fittings | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 24.06.2025
1100005538 | DRAW & MATERIAL LIST FOR WO#1100005463 | HIN-050-020-010-150-030-090 | PIPING, STEAM 80# | RECBOILER | Recovery Boilers | 23.06.2025 | 23.06.2025 | PM_I_PF | Pipe Fitters | 12.06.2025 | REESS | Scott Rees |  |  | 91100107 | Darryl Nichol | 85 | TECO | 0.00 / 485.00 / 485.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006025 | DRAW & MATERIAL LIST FOR WO#1100005463 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100005546 | 2025 KRB audit | HIN-050-020-010-150-060-010 | CONTROL, DCS | RECBOILER | Recovery Boilers | 23.06.2025 | 27.06.2025 | PM_I_IN | Instrumentation | 10.06.2025 | STILLERM | Michelle Stiller | 1 | in operation | 91100016 | Mike Kerr | 70 | Work Started | 0.00 / 3,880.00 / 2,910.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005962 | 2025 KRB audit | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100005814 | Replace backstop photoeye | HIN/022200 | RADER DRIVE THRU TRUCK DUMPER | WP | Wood Processing | 27.06.2025 | 27.06.2025 | PM_I_EL | Electrical | 26.06.2025 | DOUGLASL | Lajune Douglas | 0 | not in operation | 91100137 | Christina Chanthapanya | 85 | TECO | 0.00 / 0.00 / 722.30 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006229 | Replace backstop photoeye | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 27.06.2025
1100002193 | Replace ignitor and board | HIN/083277 | DOMESTIC HOT WATER HEATER #2 | WTREAT | Water Treatment | 23.06.2025 | 23.06.2025 | PM_I_HVA | Heating Ventilation Air Condition | 06.02.2025 | STILLERM | Michelle Stiller | 1 | in operation | 91100016 | Mike Kerr | 80 | Work Done | 0.00 / 1,390.40 / 614.40 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100002331 | Replace ignitor and board | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100004223 | FLUSH CHECK VALE/MAGE OPERATION | HIN/040Z2609 | 10% ACID PUMP DISCHARGE | BLEACH | Bleach | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2025-04-12 | TESTON | Neil Testo | 0 | not in operation | 91100020 | Carl Redahl | 85 | TECO | 0.00 / 970.00 / 1,455.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100004623 | FLUSH CHECK VALE/MAGE OPERATION | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100004513 | Tear down 40-270 pump for rebuild | HIN/04027001 | PUMP, H2S04 10 % TO PROCESS # 1 | BLEACH | Bleach | 2025-06-02 | 2025-06-04 | PM_I_RB | Rebuild Shop | 2025-04-22 | CORRIGAJ | John Corrigan | 0 | not in operation | 91100117 | Veronica Whitford | 85 | TECO | 0.00 / 1,940.00 / 1,261.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100004845 | Tear down 40-270 pump for rebuild | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100004614 | Create brackets for wall mount lights | HIN-020-020 | BROWN STOCK | BROWN | Brownstock | 2025-06-02 | 2025-06-10 | PM_I_WE | Welders | 2025-04-30 | TESTON | Neil Testo | 1 | in operation | 91100107 | Darryl Nichol | 70 | Work Started | 0.00 / 3,684.80 / 1,501.78 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100004999 | Create brackets for wall mount lights | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100001823 | NEW WO PIPING TO SAND SEPERATOR | HIN/034Z1272 | WHITE LIQUOR TO SAND SEPARATOR | DIGESTER | Digester | 2025-06-02 | 2025-06-16 | PM_I_PF | Pipe Fitters | 2025-01-24 | TESTON | Neil Testo | 1 | in operation | 91100107 | Darryl Nichol | 70 | Work Started | 0.00 / 16,371.75 / 15,206.71 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100001982 | NEW WO PIPING TO SAND SEPERATOR | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100005221 | Prep for WO 1100000066 | HIN/03413103 | MOTOR, OUTLET DEVICE # 7 | DIGESTER | Digester | 2025-06-02 | 2025-06-05 | PM_I_EL | Electrical | 2025-05-27 | TESTON | Neil Testo | 1 | in operation | 91100020 | Carl Redahl | 70 | Work Started | 0.00 / 8,730.00 / 36,884.85 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005577 | Prep for WO 1100000066 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100005160 | Fab RSA offload Pump Coupling Guard | HIN-050-010-020 | BLACK LIQUOR EVAPORATOR SYSTEM # 3 | EVAPS | Evaps/Recovery | 2025-06-02 | 2025-06-04 | PM_I_TS | Tin Smith | 2025-05-22 | PALMERT | Tyler Palmer |  |  | 91100107 | Darryl Nichol | 85 | TECO | 0.00 / 2,025.00 / 3,387.50 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005571 | Fab RSA offload Pump Coupling Guard | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100004045 | Rebuild 50-456 pump | HIN/05045601 | PUMP,CONDENSATE COLLECTING TANK 180 # | MR | Machine Room | 2025-06-02 | 2025-06-04 | PM_I_RB | Rebuild Shop | 2025-04-08 | DIRCKSC | Caleb Dircks | 1 | in operation | 91100117 | Veronica Whitford | 65 | Ready to Execute | 0.00 / 3,546.99 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100004488 | Rebuild 50-456 pump | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100004938 | Troubleshoot and repair lighting | HIN-060-020-040-100-010 | LIGHTING, ELECTRICAL SERVICES - PM1 G... | MR | Machine Room | 2025-06-02 | 2025-06-05 | PM_I_EL | Electrical | 2025-05-27 | DIRCKSC | Caleb Dircks | 1 | in operation | 91100020 | Carl Redahl | 85 | TECO | 0.00 / 8,099.80 / 1,121.75 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005545 | Troubleshoot and repair lighting | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100004939 | Program replacement Multilin | HIN/05012703 | MOTOR, VACUUM PUMP FELT UHLE BOX | MR | Machine Room | 2025-06-02 | 2025-06-03 | PM_I_EL | Electrical | 2025-05-27 | DIRCKSC | Caleb Dircks | 1 | in operation | 91100020 | Carl Redahl | 85 | TECO | 0.00 / 970.00 / 388.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005575 | Program replacement Multilin | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100005084 | OpTest ODI Scanner going offline | HIN/PM2_DIRT_DIRT_SENSOR | PM2_DIRT:DIRT SENSOR | MR | Machine Room | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2025-05-21 | DIRCKSC | Caleb Dircks | 1 | in operation | 91100020 | Carl Redahl | 85 | TECO | 0.00 / 194.00 / 388.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005365 | OpTest ODI Scanner going offline | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100005200 | Program replacement Multilin | HIN/05021303 | MOTOR, LOW PRESSURE WW SHOWERS PUMP | MR | Machine Room | 2025-06-02 | 2025-06-03 | PM_I_EL | Electrical | 2025-05-27 | DIRCKSC | Caleb Dircks | 1 | in operation | 91100020 | Carl Redahl | 85 | TECO | 0.00 / 970.00 / 388.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005576 | Program replacement Multilin | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100005204 | Re-support cable tray | HIN-060-020-040 | GENERAL PULP MACHINE | MR | Machine Room | 2025-06-02 | 2025-06-02 | PM_I_EL | Electrical | 2025-05-27 | DIRCKSC | Caleb Dircks | 1 | in operation | 91100020 | Carl Redahl | 85 | TECO | 0.00 / 776.00 / 1,130.54 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005629 | Re-support cable tray | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100005143 | Assist with Making a Difference Day | HIN-100 | MILL GENERAL | OBSOLETE | Obsolete | 2025-06-04 | 2025-06-04 | PM_I_CA | Carpenter | 2025-05-23 | CRESPEIC | Chris Crespeigne |  |  | 91100107 | Darryl Nichol | 85 | TECO | 0.00 / 970.00 / 2,231.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005601 | Assist with Making a Difference Day | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-04
1100002779 | Sodium analyzer | HIN/056Z4664 | COMBINED ANION OUTLET SODIUM CONCENTR... | PRWBOILER | Power Boilers | 2025-06-03 | 2025-06-03 | PM_I_IN | Instrumentation | 2025-02-26 | CALLIHOG | George Callihoo | 1 | in operation | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 388.00 / 776.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100003103 | Sodium analyzer | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-03
1100005388 | Reconnect power and gas to trailer | HIN-100-030-050-020 | P & R SHOP GENERAL | PRWBOILER | Power Boilers | 2025-06-05 | 2025-06-05 | PM_E_EL | External - Electrician | 2025-06-05 | KILBREAG | Gord Kilbreath | 1 | in operation | 91100079 | Michelle Stiller | 70 | Work Started | 0.00 / 388.00 / 194.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005799 | Reconnect power and gas to trailer | 2 | Rectify < 48 h |  | Standard Order | WK 23-2025 | 2025-06-05
1100005389 | Remove disconnects from splitter | HIN-050-040-040-140-050-040 | DISTRIBUTION, 347 / 575 VOLT | PRWBOILER | Power Boilers | 2025-06-06 | 2025-06-06 | PM_I_EL | Electrical | 2025-06-05 | KILBREAG | Gord Kilbreath | 1 | in operation | 91100016 | Mike Kerr | 80 | Work Done | 0.00 / 194.00 / 194.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005824 | Remove disconnects from splitter | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-06
1100004501 | Replace both filter canisters | HIN/06135611 | FILTER, SEAL WATER UNIT | RECAUST | Recaust | 2025-06-03 | 2025-06-03 | PM_I_MW | Millwright | 2025-04-21 | PALMERT | Tyler Palmer | 0 | not in operation | 91100108 | Mark Parker | 65 | Ready to Execute | 0.00 / 232.98 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100004787 | replace/repair both filters | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-03
1100005062 | replace rotating assembly | HIN/06132601 | PUMP, # 2 WEAK WASH TO # 3 REC BOILER | RECAUST | Recaust | 2025-06-03 | 2025-06-04 | PM_I_MW | Millwright | 2025-05-16 | KILBREAG | Gord Kilbreath | 1 | in operation | 91100108 | Mark Parker | 65 | Ready to Execute | 0.00 / 2,037.00 / 4,968.70 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005469 | replace rotating assembly | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-03
1100005063 | replace 61-326 suction expansion joint | HIN-050-020-010-150-030-070 | PIPING, LIQUOR | RECAUST | Recaust | 2025-06-03 | 2025-06-03 | PM_I_PF | Pipe Fitters | 2025-05-16 | KILBREAG | Gord Kilbreath | 1 | in operation | 91100108 | Mark Parker | 65 | Ready to Execute | 0.00 / 1,721.25 / 1,351.93 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005467 | replace 61-326 suction expansion joint | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-03
1100005064 | overhaul AESSEAL setup | HIN/06132601 | PUMP, # 2 WEAK WASH TO # 3 REC BOILER | RECAUST | Recaust | 2025-06-03 | 2025-06-03 | PM_I_MW | Millwright | 2025-05-16 | KILBREAG | Gord Kilbreath | 1 | in operation | 91100108 | Mark Parker | 65 | Ready to Execute | 0.00 / 1,939.26 / 1,273.48 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005468 | overhaul AESSEAL setup | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-03
1100004723 | WMTRL - REPLACE HORN AND BEACON | HIN/052Z6496B | NO. 3 EVAPORATORS REF/COND H2S | RECBOILER | Recovery Boilers | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2025-05-01 | FRATTINK | Kim Frattinger | 1 | in operation | 91100079 | Michelle Stiller | 85 | TECO | 0.00 / 3,441.33 / 5,186.83 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005077 | REPLACE HORN AND BEACON | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100005222 | RB3 IK25 REPLACE TRACKS | HIN/05212611 | SOOTBLOWER, #25 | RECBOILER | Recovery Boilers | 2025-06-03 | 2025-06-03 | PM_I_MW | Millwright | 2025-05-27 | KILBREAG | Gord Kilbreath | 1 | in operation | 91100108 | Mark Parker | 85 | TECO | 0.00 / 9,910.96 / 0.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005640 | RB3 IK25 overhaul | 2 | Rectify < 48 h |  | Standard Order | WK 23-2025 | 2025-06-03
1100005258 | RB3 IK9 replace poppet valve | HIN/05211011 | SOOTBLOWER, #9 | RECBOILER | Recovery Boilers | 2025-06-03 | 2025-06-03 | PM_I_PF | Pipe Fitters | 2025-05-28 | KILBREAG | Gord Kilbreath | 1 | in operation | 91100108 | Mark Parker | 85 | TECO | 0.00 / 1,570.63 / 2,336.50 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005648 | RB3 IK9 replace poppet valve | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-03
1100005259 | RB3 IK46 replace poppet valve | HIN/05214711 | SOOTBLOWER, #46 | RECBOILER | Recovery Boilers | 2025-06-03 | 2025-06-03 | PM_I_PF | Pipe Fitters | 2025-05-28 | KILBREAG | Gord Kilbreath | 1 | in operation | 91100108 | Mark Parker | 85 | TECO | 0.00 / 1,570.63 / 2,336.50 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005649 | RB3 IK46 replace poppet valve | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-03
1100005280 | RB3 IK26 replace poppet valve | HIN/05212711 | SOOTBLOWER, #26 | RECBOILER | Recovery Boilers | 2025-06-03 | 2025-06-03 | PM_I_PF | Pipe Fitters | 2025-05-28 | KILBREAG | Gord Kilbreath | 1 | in operation | 91100108 | Mark Parker | 85 | TECO | 0.00 / 1,570.63 / 2,336.52 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005660 | RB3 IK26 replace poppet valve | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-03
1100005137 | Fan blade orientation wrong | HIN/015425 | VENTILATION FAN 2ND FLOOR | WP | Wood Processing | 2025-06-03 | 2025-06-03 | PM_I_MW | Millwright | 2025-05-27 | DOUGLASL | Lajune Douglas |  |  | 91100108 | Mark Parker | 65 | Ready to Execute | 0.00 / 873.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005622 | replace entire fan | 2 | Rectify < 48 h |  | Standard Order | WK 23-2025 | 2025-06-03
1100005246 | belt brush is not functioning - verify | HIN/015141 | AIR KNIFE FOR 15 134 | WP | Wood Processing | 2025-06-02 | 2025-06-02 | PM_I_EL | Electrical | 2025-05-27 | DOUGLASL | Lajune Douglas | 1 | in operation | 91100016 | Mike Kerr | 85 | TECO | 0.00 / 970.00 / 414.66 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005607 | The belt brush is not functioning verify | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100005253 | Center troughing roll failed | HIN/022162 | CHIP ACCEPTS CONVEYOR | WP | Wood Processing | 2025-06-03 | 2025-06-03 | PM_I_MW | Millwright | 2025-05-28 | DOUGLASL | Lajune Douglas |  |  | 91100108 | Mark Parker | 85 | TECO | 0.00 / 2,906.38 / 0.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005639 | Center troughing roll failed | 1 | Immediately < 24h |  | Standard Order | WK 23-2025 | 2025-06-03
1100005651 | Replace transmitter | HIN/038Z1584 | PRIMARY SCREEN 1 & 2, FEED | BROWN | Brownstock | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 23.06.2025 | DALLAIRB | Brady Dallaire |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 2,503.81 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006177 | Replace transmitter | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 23.06.2025
1100005749 | install spades for vessel lockout | HIN/038219 | WASHER # 1A | BROWN | Brownstock | 24.06.2025 | 24.06.2025 | PM_I_PF | Pipe Fitters | 24.06.2025 | POWERSM | Mitch Powers |  |  |  |  | 65 | Ready to Execute | 0.00 / 0.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006230 | install spades for vessel lockout | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 24.06.2025
1100005793 | 38401 HVAC unit Comp #2 | HIN/038401 | A/C UNIT ELEC ROOM | BROWN | Brownstock | 25.06.2025 | 25.06.2025 | PM_I_EL | Electrical | 25.06.2025 | TESTON | Neil Testo |  |  |  |  | 70 | Work Started | 0.00 / 1,940.00 / 1,940.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006137 | 38401 HVAC unit Comp #2 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 25.06.2025
1100005797 | Replaced consistency paddle | HIN/038Z1501 | STOCK FROM BLOW TANK TO 1A KNOTTERS C... | BROWN | Brownstock | 26.06.2025 | 26.06.2025 | PM_I_IN | Instrumentation | 26.06.2025 | TESTON | Neil Testo | 1 | in operation |  |  | 80 | Work Done | 0.00 / 9,502.50 / 721.39 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006212 | Replaced consistency paddle | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 26.06.2025
1100005803 | 34-lc-1600 on 1 a washer plugged | HIN/038Z1600 | #1A WASHER | BROWN | Brownstock | 24.06.2025 | 24.06.2025 | PM_I_IN | Instrumentation | 24.06.2025 | WRIGHTM | Mark Wright |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 145.50 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006223 | 34-lc-1600 on 1 a washer plugged | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 24.06.2025
1100000696 | Sosperse new pipe | HIN-020-010-120-070-050 | PIPING, CHEMICAL | DIGESTER | Digester | 23.06.2025 | 23.06.2025 | PM_I_PF | Pipe Fitters | 10.12.2024 | TESTON | Neil Testo | 1 | in operation |  |  | 85 | TECO | 0.00 / 1,233.88 / 1,427.65 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100000804 | Sosperse new pipe | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100005748 | VIBS FOUND INBOARD MOTOR BEARING FAILING | HIN/03416403 | MOTOR, CONDENSATE RETURN | DIGESTER | Digester | 23.06.2025 | 23.06.2025 | PM_I_EL | Electrical | 23.06.2025 | TESTON | Neil Testo |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 3,240.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006198 | VIBS FOUND INBOARD MOTOR BEARING FAILING | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 23.06.2025
1100005750 | actuator hanging, bolts backed out | HIN/034Z1225 | LEVEL - CONTROL - DIGESTER LEVEL TANK | DIGESTER | Digester | 24.06.2025 | 24.06.2025 | PM_I_IN | Instrumentation | 24.06.2025 | POWERSM | Mitch Powers |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 280.54 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006231 | actuator hanging, bolts backed out | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 24.06.2025
1100005779 | Remove #1 BC Heater Bottom Lid/Cap | HIN/034PRV16 | HEATER, BOTTOM CIRCULATION # 1 | DIGESTER | Digester | 27.06.2025 | 27.06.2025 | PM_I_PF | Pipe Fitters | 27.06.2025 | MYCKT | Tyler Myck |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 412.34 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006248 | Remove #1 BC Heater Bottom Lid/Cap | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 27.06.2025
1100005789 | REMOVE BROKEN TIN STACK | HIN-020-010-120-020 | BUILDINGS, DIGESTER | DIGESTER | Digester | 24.06.2025 | 24.06.2025 | PM_I_TS | Tin Smith | 24.06.2025 | TESTON | Neil Testo |  |  |  |  | 65 | Ready to Execute | 0.00 / 0.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006251 | REMOVE BROKEN TIN STACK | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 24.06.2025
1100004962 | RPLC Valve in sealed sewer | HIN-050-010-020-210-020-030 | SEWERS, | EVAPS | Evaps/Recovery | 24.06.2025 | 25.06.2025 | PM_I_PF | Pipe Fitters | 15.05.2025 | BLEACKLJ | Josh Bleackley | 1 | in operation |  |  | 70 | Work Started | 0.00 / 1,670.00 / 2,867.01 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005354 | Rplc Packing in Sealed Sewer Valve | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 24.06.2025
1100005628 | Replace HPD 70% piping (recaust) | HIN-050-010-020-210-030-060 | PIPING, LIQUOR | EVAPS | Evaps/Recovery | 24.06.2025 | 24.06.2025 | PM_I_PF | Pipe Fitters | 19.06.2025 | BLEACKLJ | Josh Bleackley |  |  |  |  | 85 | TECO | 0.00 / 7,048.92 / 4,121.69 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006142 | Replace HPD 70% piping (recaust) | 1 | Immediately < 24h |  | Standard Order | WK 26-2025 | 24.06.2025
1100005693 | Troubleshoot valve | HIN/051Z6579 | STRIPPER GAS WARM UP/ MAKE UP STEAM | EVAPS | Evaps/Recovery | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 22.06.2025 | DALLAIRB | Brady Dallaire |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 9,348.90 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006210 | Troubleshoot valve | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 23.06.2025
1100005812 | REPAIR TURPENTINE PUMP D/N TURN | HIN/051212 | TURPENTINE PUMP, TO #2 RECOVERY | EVAPS | Evaps/Recovery | 25.06.2025 | 25.06.2025 | PM_I_MW | Millwright | 25.06.2025 | BLEACKLJ | Josh Bleackley |  |  |  |  | 65 | Ready to Execute | 0.00 / 0.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006271 | REPAIR TURPENTINE PUMP D/N TURN | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 25.06.2025
1100005758 | KILN STACK 3 MTH OPACITY | HIN-040-020-080-040 | LOOPS, LIME KILN SCRUBBER SYSTEM | KILN | Lime Kiln | 25.06.2025 | 26.06.2025 | PM_I_IN | Instrumentation | 25.06.2025 | MACKAYL | Launy MacKay |  |  |  |  | 65 | Ready to Execute | 0.00 / 291.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006265 | KILN STACK 3 MTH OPACITY | 1 | Immediately < 24h |  | Standard Order | WK 26-2025 | 25.06.2025
1100005764 | WO for Kiln Trunnion Rebuild | HIN-040-020-030 | KILN, LIME | KILN | Lime Kiln | 23.06.2025 | 23.06.2025 | PM_I_EN | Engineer | 23.06.2025 | BLEACKLJ | Josh Bleackley |  |  |  |  | 65 | Ready to Execute | 0.00 / 0.00 / 8,555.65 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006084 | WO for Kiln Trunnion Rebuild | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100005765 | WO for Kiln Trunnion Rebuild | HIN-040-020-030 | KILN, LIME | KILN | Lime Kiln | 23.06.2025 | 23.06.2025 | PM_I_EN | Engineer | 23.06.2025 | BLEACKLJ | Josh Bleackley |  |  |  |  | 65 | Ready to Execute | 0.00 / 0.00 / 8,555.65 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006085 | WO for Kiln Trunnion Rebuild | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100004687 | Leachate Unit#380 Heater Control | HIN/MOB041 | TRUCK, LEACHATE DISPOSAL UNIT 380 | MOB | Mobile | 23.06.2025 | 23.06.2025 | PM_I_HDM | Heavy Duty Mechanics | 01.05.2025 | DOUGLASL | Lajune Douglas |  |  |  |  | 65 | Ready to Execute | 0.00 / 2,622.10 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005055 | Leachate Unit#380 Heater Control | 1 | Immediately < 24h |  | Standard Order | WK 26-2025 | 23.06.2025
1100005250 | Rear Light bar | HIN/MOB168 | UNIT # 168 2018 CASE QUADTRAC CHIP DOZER | MOB | Mobile | 23.06.2025 | 23.06.2025 | PM_I_HDM | Heavy Duty Mechanics | 28.05.2025 | DOUGLASL | Lajune Douglas |  |  |  |  | 65 | Ready to Execute | 0.00 / 388.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005681 | Rear Light bar | 1 | Immediately < 24h |  | Standard Order | WK 26-2025 | 23.06.2025
1100001809 | Repair damaged wall and install door | HIN-060-020-040 | GENERAL PULP MACHINE | MR | Machine Room | 23.06.2025 | 23.06.2025 | PM_E_CA | External - Carpenter | 24.01.2025 | DIRCKSC | Caleb Dircks |  |  |  |  | 65 | Ready to Execute | 0.00 / 14,596.86 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100001993 | Repair damaged wall and install door | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100004667 | Leak detect and repair. | HIN/05071909 | COMPRESSOR, AC UNIT #1 MCC ROOM | MR | Machine Room | 23.06.2025 | 24.06.2025 | PM_I_HVA | Heating Ventilation Air Condition | 29.04.2025 | DIRCKSC | Caleb Dircks | 1 | in operation |  |  | 85 | TECO | 0.00 / 2,910.00 / 3,011.38 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100004990 | Leak detect and repair. | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100004732 | Install valve handles | HIN-060-020-040-080-040 | PIPING, CONDENSATE | MR | Machine Room | 23.06.2025 | 24.06.2025 | PM_I_PF | Pipe Fitters | 01.05.2025 | DIRCKSC | Caleb Dircks | 1 | in operation |  |  | 85 | TECO | 0.00 / 776.00 / 388.28 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005080 | Rebuild or replace 5 cond valves | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100005653 | Troubleshoot Function of Elevator | HIN/04916211 | ELEVATOR, FREIGHT MACHINE ROOM | MR | Machine Room | 23.06.2025 | 23.06.2025 | PM_E_EL | External - Electrician | 24.06.2025 | ZYGMUNTB | Bryan Zygmunt |  |  |  |  | 65 | Ready to Execute | 0.00 / 0.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006179 | Troubleshoot Function of Elevator | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 23.06.2025
1100005739 | 2nd Press Sheet Break Investigation | HIN/050Z372242 | DETECTOR, SHEET BREAK, 050AI3722 | MR | Machine Room | 23.06.2025 | 24.06.2025 | PM_I_EL | Electrical | 19.06.2025 | DIRCKSC | Caleb Dircks | 1 | in operation |  |  | 85 | TECO | 0.00 / 970.00 / 1,940.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006108 | 2nd Press Sheet Break Investigation | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 23.06.2025
1100005766 | XFRMR Room alarming temp | HIN/050Z382842 | SWITCH, TEMPERATURE, PM #2 XFMR ROOM ... | MR | Machine Room | 23.06.2025 | 23.06.2025 | PM_I_IN | Instrumentation | 23.06.2025 | MCEACHJO | Josh Mceachern |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 388.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006205 | XFRMR Room alarming temp | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 23.06.2025
1100005805 | North MCC Alarming hot | HIN/050Z3834 | PM #2 MCC ROOM TEMPERATURE SWITCH HIG... | MR | Machine Room | 25.06.2025 | 25.06.2025 | PM_I_HVA | Heating Ventilation Air Condition | 25.06.2025 | WRIGHTM | Mark Wright |  |  |  |  | 80 | Work Done | 0.00 / 0.00 / 1,731.02 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006227 | North MCC Alarming hot | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 25.06.2025
1100005697 | South #2 T/R set lost power | HIN/053134 | TRANSFORMER, T/R SET #2 CHAMBER #2 | PRECIPS | Precips | 26.06.2025 | 26.06.2025 | PM_I_EL | Electrical | 26.06.2025 | FENRICHD | David Fenrich |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 194.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006269 | South #2 T/R set lost power | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 26.06.2025
1100005652 | Pinhole Fire Main Leak | HIN-050-100-040-030-010 | SPRINKLERS | PRWBOILER | Power Boilers | 23.06.2025 | 23.06.2025 | PM_I_PF | Pipe Fitters | 24.06.2025 | ZYGMUNTB | Bryan Zygmunt |  |  |  |  | 65 | Ready to Execute | 0.00 / 0.00 / 77.71 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006178 | Pinhole Fire Main Leak | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 23.06.2025
1100005654 | troubleshoot burner tripping | HIN/056Z4574 | BURNER #1 VALVE (SSV-222) POSITION _B... | PRWBOILER | Power Boilers | 24.06.2025 | 24.06.2025 | PM_I_IN | Instrumentation | 24.06.2025 | DALLAIRB | Brady Dallaire |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 2,468.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006220 | troubleshoot burner tripping | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 24.06.2025
1100005752 | Need the grates measuring stick fixed | HIN/059104 | NORTH STOKER GRATE, HOG BOILER | PRWBOILER | Power Boilers | 25.06.2025 | 25.06.2025 | PM_I_MW | Millwright | 25.06.2025 | SMICOL | Colin Smith |  |  |  |  | 80 | Work Done | 0.00 / 0.00 / 291.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006233 | Need the grates measuring stick fixed | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 25.06.2025
1100005813 | Motion switch replacement | HIN/059192 | ROTARY FEEDER, # 3 SOUTH MULTICONE | PRWBOILER | Power Boilers | 26.06.2025 | 26.06.2025 | PM_I_EL | Electrical | 26.06.2025 | FENRICHD | David Fenrich |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 912.93 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006274 | Motion switch replacement | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 26.06.2025
1100004633 | RB3 IK1 replace poppet valve | HIN/05210211 | SOOTBLOWER, #1 | RECBOILER | Recovery Boilers | 24.06.2025 | 24.06.2025 | PM_I_PF | Pipe Fitters | 29.04.2025 | FRATTINK | Kim Frattinger | 1 | in operation |  |  | 85 | TECO | 0.00 / 2,724.51 / 12.84 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005030 | RB3 IK1 replace poppet valve | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 24.06.2025
1100005756 | RB 3 QUARTERLY OPACITY | HIN-050-020-010-140-100 | FLUE GAS, HANDLING SYSTEM | RECBOILER | Recovery Boilers | 25.06.2025 | 26.06.2025 | PM_I_IN | Instrumentation | 25.06.2025 | MACKAYL | Launy MacKay |  |  |  |  | 80 | Work Done | 0.00 / 291.00 / 291.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006264 | RB 3 QUARTLY OPACITY | 1 | Immediately < 24h |  | Standard Order | WK 26-2025 | 25.06.2025
1100005757 | MAIN STACK 3 MTH OPACITY | HIN-050-020-020-180-240 | LOOPS, FLUE GAS RB2 | RECBOILER | Recovery Boilers | 25.06.2025 | 26.06.2025 | PM_I_IN | Instrumentation | 25.06.2025 | MACKAYL | Launy MacKay |  |  |  |  | 80 | Work Done | 0.00 / 291.00 / 387.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006263 | MAIN STACK 3 MTH OPACITY | 1 | Immediately < 24h |  | Standard Order | WK 26-2025 | 25.06.2025
1100005826 | Repair spout #2 door hinge | HIN/052TNK11 | TANK, MAIN DISSOLVING | RECBOILER | Recovery Boilers | 26.06.2025 | 26.06.2025 | PM_I_PF | Pipe Fitters | 26.06.2025 | OPSTEENJ | Johan Opsteen |  |  |  |  | 65 | Ready to Execute | 0.00 / 0.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006289 | Repair spout #2 door hinge | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 26.06.2025
1100005694 | leak on clamp. need for loading today | HIN-090-020-040 | MOBILE, RENTAL FORKLIFTS | WP | Wood Processing | 23.06.2025 | 23.06.2025 | PM_I_MW | Millwright | 23.06.2025 | ERICKSOT | Todd Erickson |  |  |  |  | 80 | Work Done | 0.00 / 0.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100006213 | leak on clamp. need for loading today | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 23.06.2025
1100005768 | Backstop Sensor broken off | HIN-010-050-010 | MAIN DUMPER | WP | Wood Processing | 24.06.2025 | 24.06.2025 | PM_I_EL | Electrical | 24.06.2025 | FENRICHD | David Fenrich |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 1,040.37 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006207 | Backstop Sensor broken off | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 24.06.2025
1100005769 | Replace 2 Blown 225amp Fuses | HIN/015330 | SCREEN, SECONDARY EAST LIWELL | WP | Wood Processing | 24.06.2025 | 24.06.2025 | PM_I_EL | Electrical | 24.06.2025 | FENRICHD | David Fenrich |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 532.75 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100006208 | Replace 2 Blown 225amp Fuses | 1 | Immediately < 24h | E | Emergency Order | WK 26-2025 | 24.06.2025
1100004674 | Prepare pump for rebuild 1100000794 | HIN/08318601 | PUMP, # 4 FILTERED WATER TO MILL | WTREAT | Water Treatment | 25.06.2025 | 26.06.2025 | PM_I_MW | Millwright | 30.04.2025 | DOUGLASL | Lajune Douglas |  |  |  |  | 85 | TECO | 0.00 / 3,298.00 / 4,186.40 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005046 | Prepare pump for rebuild 1100000794 | 3 | Planned exec. > 48 h |  | Standard Order | WK 26-2025 | 25.06.2025
1100005335 | Reset Overloaded Elevator | HIN/04113911 | ELEVATOR, BLEACH FREIGHT | BLEACH | Bleach | 2025-06-05 | 2025-06-05 | PM_E_EL | External - Electrician | 2025-06-05 | ZYGMUNTB | Bryan Zygmunt |  |  |  |  | 65 | Ready to Execute | 0.00 / 0.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005835 | Reset Overloaded Elevator | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-05
1100002902 | 38-215 TERTIARY SCREEN INSPECTION | HIN/03821511 | SCREEN, TERTIARY SCREEN | BROWN | Brownstock | 2025-06-02 | 2025-06-10 | PM_I_MW | Millwright | 2025-02-28 | TESTON | Neil Testo | 1 | in operation |  |  | 65 | Ready to Execute | 0.00 / 18,516.46 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100003199 | 38-215 TERTIARY SCREEN INSPECTION | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100004762 | 4A Washer Wire and Valve | HIN/03828812 | WASHER, DRUM # 4 A | BROWN | Brownstock | 2025-06-02 | 2025-06-10 | PM_I_MW | Millwright | 2025-05-02 | CRESPEIC | Chris Crespeigne | 8 | Next Planned Shut |  |  | 65 | Ready to Execute | 0.00 / 30,516.47 / 1,793.22 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005124 | 4A Washer Wire and Valve | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100005232 | 10% ACID TIE-IN TO 4A STANDPIPE | HIN-020-020-140-010 | STANDPIPE, # 4 A | BROWN | Brownstock | 2025-06-02 | 2025-06-05 | PM_I_PF | Pipe Fitters | 2025-05-28 | TESTON | Neil Testo | 1 | in operation |  |  | 85 | TECO | 0.00 / 6,597.46 / 4,542.16 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005710 | 10% ACID TIE-IN TO 4A STANDPIPE | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100005233 | 10% ACID TIE-IN TO 4B STANDPIPE | HIN-020-020-150-010 | STANDPIPE, # 4B | BROWN | Brownstock | 2025-06-05 | 2025-06-10 | PM_I_PF | Pipe Fitters | 2025-05-28 | TESTON | Neil Testo |  |  |  |  | 70 | Work Started | 0.00 / 3,240.00 / 2,910.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005711 | 10% ACID TIE-IN TO 4B STANDPIPE | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-05
1100005297 | Investigat control loop issues | HIN/038Z1754 | FILTRATE TO OXYGEN REACTOR | BROWN | Brownstock | 2025-06-04 | 2025-06-04 | PM_I_IN | Instrumentation | 2025-06-04 | WILGENBE | Erin Wilgenbusch |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 388.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005827 | Investigat control loop issues | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-04
1100005302 | 38-213 sec screen motor grounded. | HIN/03821303 | MOTOR, SECONDARY SCREEN # 1 | BROWN | Brownstock | 2025-06-02 | 2025-06-02 | PM_I_MW | Millwright | 2025-06-02 | WRIGHTM | Mark Wright |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 864.92 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005749 | 38-213 sec screen motor grounded. | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-02
1100005303 | replace belts | HIN/03820911 | SCREEN, PRIMARY # 1 | BROWN | Brownstock | 2025-06-02 | 2025-06-02 | PM_I_MW | Millwright | 2025-06-02 | MCCRACKM | Mike McCracken |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 1,476.68 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005770 | replace belts | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-02
1100005304 | 4 B standpipe level control valve. | HIN/038Z1866 | #4A STANDPIPE | BROWN | Brownstock | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2025-06-02 | WRIGHTM | Mark Wright |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 3,014.28 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005771 | 4 B standpipe level control valve. | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-02
1100005305 | disconnect 38-210 sec screen motor | HIN/03821003 | MOTOR, PRIMARY SCREEN # 2 | BROWN | Brownstock | 2025-06-02 | 2025-06-02 | PM_I_EL | Electrical | 2025-06-02 | WRIGHTM | Mark Wright |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 261.90 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005772 | disconnect 38-210 sec screen motor | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-02
1100005322 | REMOVE REBUILD REPLACE 381876 | HIN-020-020-150-010 | STANDPIPE, # 4B | BROWN | Brownstock | 2025-06-03 | 2025-06-03 | PM_I_PF | Pipe Fitters | 2025-06-03 | TESTON | Neil Testo |  |  |  |  | 80 | Work Done | 0.00 / 0.00 / 2,060.15 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005800 | REMOVE REBUILD REPLACE 381876 | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-03
1100005306 | 34-FC-1241 stuck at 75% | HIN/034Z1241 | HIGH PRESSURE FEEDER PURGE FLOW | DIGESTER | Digester | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2025-06-02 | WRIGHTM | Mark Wright |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 0.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005774 | 34-FC-1241 stuck at 75% | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-02
1100005307 | Replace pilot | HIN/034Z1241 | HIGH PRESSURE FEEDER PURGE FLOW | DIGESTER | Digester | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2025-06-03 | WILGENBE | Erin Wilgenbusch |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 1,511.67 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005779 | Replace pilot | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-02
1100005218 | PKU392 Rad is leaking | HIN/PKU392 | VEHICLE, 2019, FORD, F350 CREW CAB 4X... | MOB | Mobile | 2025-06-02 | 2025-06-02 | PM_I_HDM | Heavy Duty Mechanics | 2025-05-30 | DOUGLASL | Lajune Douglas |  |  |  |  | 85 | TECO | 0.00 / 1,940.00 / 0.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005728 | PKU392 Rad is leaking | 1 | Immediately < 24h |  | Standard Order | WK 23-2025 | 2025-06-02
1100005219 | MOB#168 Hyd Arm Leak. | HIN/MOB168 | UNIT # 168 2018 CASE QUADTRAC CHIP DOZER | MOB | Mobile | 2025-06-02 | 2025-06-02 | PM_I_HDM | Heavy Duty Mechanics | 2025-06-01 | SWAINT | Tyson Swain |  |  |  |  | 80 | Work Done | 0.00 / 0.00 / 2,960.40 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005696 | MOB#168 Hyd Arm Leak. | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-02
1100005244 | back lights need replaced. burned out | HIN/MOB035 | TRACKMOBILE UNIT 148 | MOB | Mobile | 2025-06-04 | 2025-06-04 | PM_I_HDM | Heavy Duty Mechanics | 2025-05-27 | DOUGLASL | Lajune Douglas |  |  |  |  | 80 | Work Done | 0.00 / 485.00 / 485.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005653 | back lights need replaced. burned out | 2 | Rectify < 48 h |  | Standard Order | WK 23-2025 | 2025-06-04
1100005311 | 1000 Hr Service tractor 169 | HIN/MOB169 | MOB169 - 2018 CASE QUAD TRAC 620 | MOB | Mobile | 2025-06-05 | 2025-06-05 | PM_I_HDM | Heavy Duty Mechanics | 2025-06-05 | DOUGLASL | Lajune Douglas |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 1,117.53 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005826 | 1000 Hr Service tractor 169 | 1 | Immediately < 24h |  | Standard Order | WK 23-2025 | 2025-06-05
1100005279 | Adjust High High Limit Switch | HIN/049177 | CRANE, BRIDGE | MR | Machine Room | 2025-06-03 | 2025-06-03 | PM_E_EL | External - Electrician | 2025-06-03 | ZYGMUNTB | Bryan Zygmunt |  |  |  |  | 65 | Ready to Execute | 0.00 / 0.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005788 | Adjust High High Limit Switch | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-03
1100005300 | Troubleshoot VFD Failure | HIN/050240 | CUTTER, WET END TAIL DRIVE SIDE | MR | Machine Room | 2025-06-02 | 2025-06-02 | PM_I_EL | Electrical | 2025-06-01 | KEMPIND | Duane Kempin |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 582.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005747 | Troubleshoot VFD Failure | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-02
1100005301 | Troubleshoot VFD Failure | HIN/050240 | CUTTER, WET END TAIL DRIVE SIDE | MR | Machine Room | 2025-06-02 | 2025-06-02 | PM_I_EL | Electrical | 2025-06-01 | KEMPIND | Duane Kempin |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 970.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005748 | Troubleshoot VFD Failure | 2 | Rectify < 48 h | E | Emergency Order | WK 23-2025 | 2025-06-02
1100005315 | repair | HIN-060-020-040-010 | EQUIPMENT, GENERAL | MR | Machine Room | 2025-06-06 | 2025-06-06 | PM_I_MW | Millwright | 2025-06-06 | TESKEYD | Dean Teskey |  |  |  |  | 65 | Ready to Execute | 0.00 / 0.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005870 | repair | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-06
1100005310 | repair | HIN-070 | PULP WAREHOUSE | PLPWRHSE | Pulp Warehouse | 2025-06-05 | 2025-06-05 | PM_I_EL | Electrical | 2025-06-05 | TESKEYD | Dean Teskey |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 582.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005840 | repair | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-05
1100005331 | disconnect power and gas | HIN-100-030-050-020 | P & R SHOP GENERAL | PRWBOILER | Power Boilers | 2025-06-04 | 2025-06-04 | PM_I_EL | Electrical | 2025-06-04 | MACKAYL | Launy MacKay |  |  |  |  | 85 | TECO | 0.00 / 1,376.00 / 0.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005808 | disconnect power and gas | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-04
1100005333 | Create a drawing for WO 1100005385 | HIN-050-030-040-010-010 | PIPING, WATER | PRWBOILER | Power Boilers | 2025-06-05 | 2025-06-06 | PM_I_PF | Pipe Fitters | 2025-06-04 | KILBREAG | Gord Kilbreath | 1 | in operation |  |  | 80 | Work Done | 0.00 / 485.00 / 97.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005830 | Create a drawing for WO 1100005385 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-05
1100005296 | Replace belts on mud filter exhaust fan | HIN/061318 | LMPF VENT FAN, | RECAUST | Recaust | 2025-06-04 | 2025-06-04 | PM_I_MW | Millwright | 2025-06-04 | WARRINEA | Alex Warriner |  |  |  |  | 65 | Ready to Execute | 0.00 / 0.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005825 | Replace belts on mud filter exhaust fan | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-04
1100005309 | Install Blinds on Suction/Dis of 61-330 | HIN/061330 | # 1 WEAK ACID TRANSFER PUMP | RECAUST | Recaust | 2025-06-04 | 2025-06-04 | PM_I_PF | Pipe Fitters | 2025-06-04 | BLEACKLJ | Josh Bleackley |  |  |  |  | 80 | Work Done | 0.00 / 0.00 / 632.60 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005798 | Install Blinds on Suction/Dis of 61-330 | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-04
1100005316 | #4 Caustisizer Level is drifting | HIN/061Z7522 | #4 CAUSTICIZER LEVEL CONTROL | RECAUST | Recaust | 2025-06-06 | 2025-06-06 | PM_I_IN | Instrumentation | 2025-06-06 | BLEACKLJ | Josh Bleackley |  |  |  |  | 80 | Work Done | 0.00 / 0.00 / 776.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005871 | #4 Caustisizer Level is drifting | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-06
1100005423 | Install 40HP Motor on 61-332 | HIN/06133203 | MOTOR, # 2 WEAK ACID TRANSFER | RECAUST | Recaust | 2025-06-06 | 2025-06-06 | PM_I_MW | Millwright | 2025-06-06 | BLEACKLJ | Josh Bleackley |  |  |  |  | 80 | Work Done | 0.00 / 0.00 / 5,500.22 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005873 | Install 40HP Motor on 61-332 | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-06
1100005424 | Replace Belts on LMPF Exh. Fan. | HIN/061M318 | LIME MUD PRESSURE FILTER EXHAUST FAN | RECAUST | Recaust | 2025-06-06 | 2025-06-06 | PM_I_MW | Millwright | 2025-06-06 | BLEACKLJ | Josh Bleackley |  |  |  |  | 80 | Work Done | 0.00 / 0.00 / 390.97 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005874 | Replace Belts on LMPF Exh. Fan. | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-06
1100005425 | Replace Belts on WLPF Exh. Fan | HIN/061M304 | WHITE LIQUOR PRESSURE FILTER EXHAUST FAN | RECAUST | Recaust | 2025-06-06 | 2025-06-06 | PM_I_MW | Millwright | 2025-06-06 | BLEACKLJ | Josh Bleackley |  |  |  |  | 80 | Work Done | 0.00 / 0.00 / 48.50 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005875 | Replace Belts on WLPF Exh. Fan | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-06
1100005291 | Troubleshoot air conditioner | HIN/052288 | AIR CONDITIONER UNIT MCC ROOM | RECBOILER | Recovery Boilers | 2025-06-03 | 2025-06-03 | PM_I_EL | Electrical | 2025-06-03 | WILGENBE | Erin Wilgenbusch |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 493.84 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005768 | Troubleshoot air conditioner | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-03
1100005314 | RB3 IK44 replace packing | HIN/05214511 | SOOTBLOWER, #44 | RECBOILER | Recovery Boilers | 2025-06-05 | 2025-06-05 | PM_I_MW | Millwright | 2025-06-06 | OPSTEENJ | Johan Opsteen |  |  |  |  | 80 | Work Done | 0.00 / 0.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005849 | RB3 IK44 replace packing | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-05
1100005320 | Troubleshoot LB2 ignitor | HIN/055Z5538B | IGNITOR OFF LB2 | RECBOILER | Recovery Boilers | 2025-06-02 | 2025-06-02 | PM_I_IN | Instrumentation | 2025-06-01 | DALLAIRB | Brady Dallaire |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 2,565.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005697 | Troubleshoot LB2 ignitor | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-02
1100005321 | Port rodder s4 bypassing | HIN-050 | POWER AND RECOVERY | RECBOILER | Recovery Boilers | 2025-06-02 | 2025-06-02 | PM_I_PF | Pipe Fitters | 2025-06-01 | SMICOL | Colin Smith |  |  |  |  | 80 | Work Done | 0.00 / 0.00 / 388.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005698 | Port rodder s4 bypassing | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-02
1100005368 | RB3 Ik25 replace poppet and trip bar | HIN/05212611 | SOOTBLOWER, #25 | RECBOILER | Recovery Boilers | 2025-06-06 | 2025-06-06 | PM_I_MW | Millwright | 2025-06-06 | CALLIHOG | George Callihoo |  |  |  |  | 80 | Work Done | 0.00 / 0.00 / 2,326.27 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005758 | RB3 Ik25 replace poppet and trip bar | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-06
1100005369 | RB3 Ik25 replace packing | HIN/05212611 | SOOTBLOWER, #25 | RECBOILER | Recovery Boilers | 2025-06-06 | 2025-06-06 | PM_I_MW | Millwright | 2025-06-06 | CALLIHOG | George Callihoo |  |  |  |  | 80 | Work Done | 0.00 / 0.00 / 97.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005759 | RB3 Ik25 replace packing | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-06
1100001729 | Build collection system for leak | HIN-100-060-020-030 | BUILDINGS, LAB | TECHNICAL | Technical | 2025-06-02 | 2025-06-04 | PM_I_MW | Millwright | 2025-01-22 | DIRCKSC | Caleb Dircks | 1 | in operation |  |  | 85 | TECO | 0.00 / 1,940.00 / 291.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100001877 | Build collection system for leak | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100004884 | Pins coming out | HIN/022163 | RECLAIM FROM STORAGE | WP | Wood Processing | 2025-06-02 | 2025-06-03 | PM_I_MW | Millwright | 2025-05-09 | DOUGLASL | Lajune Douglas |  |  |  |  | 85 | TECO | 0.00 / 1,940.00 / 0.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005235 | Pins coming out | 2 | Rectify < 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100005216 | Modify return trainer bracket for 15-134 | HIN/01513405 | CONVEYOR, CHIPS FROM SILOS | WP | Wood Processing | 2025-06-02 | 2025-06-02 | PM_I_WE | Welders | 2025-05-30 | DOUGLASL | Lajune Douglas |  |  |  |  | 65 | Ready to Execute | 0.00 / 291.00 / 0.00 CAD | 2 | Released | YA01 | Reactive Maintenance | 9100005693 | Modify return trainer bracket for 15-134 | 3 | Planned exec. > 48 h |  | Standard Order | WK 23-2025 | 2025-06-02
1100005295 | Repair hydraulic leak Unit 11653 | HIN-090-020-040 | MOBILE, RENTAL FORKLIFTS | WP | Wood Processing | 2025-06-03 | 2025-06-04 | PM_I_HDM | Heavy Duty Mechanics | 2025-06-03 | BOHNINGB | Bruce Bohning |  |  |  |  | 85 | TECO | 0.00 / 970.00 / 0.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005820 | Repair hydraulic leak Unit 11653 | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-03
1100005329 | replace belts | HIN/021115 | Hog Metering Screw Conveyor | WP | Wood Processing | 2025-06-03 | 2025-06-03 | PM_I_MW | Millwright | 2025-06-03 | CALLIHOT | Travis Callihoo |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 0.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005804 | replace belts | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-03
1100005359 | Replace drive belts | HIN/02111505 | Metering Screw Conveyor | WP | Wood Processing | 2025-06-03 | 2025-06-03 | PM_I_MW | Millwright | 2025-06-03 | ECCLESTD | Douglas Eccleston |  |  |  |  | 85 | TECO | 0.00 / 0.00 / 291.00 CAD | 3 | Technically Completed | YA01 | Reactive Maintenance | 9100005811 | Replace drive belts | 1 | Immediately < 24h | E | Emergency Order | WK 23-2025 | 2025-06-03